## Sheet1
Title | Category | Dock list number | Reference drawing | Description | Location | Specification | Requisition number | Milestone | Assigned to | Collaborators | Status | Priority | Start Date | Deadline | Budget | Gas free certificate | Light | Ventilation | Crane assistance | Cleaning before | Cleaning after | Work permit | Painting after completion | Parts on board | Transport to yard workshop | Transport outside yard | Material yards supply | Material owners supply | Risk assessment | Marker | Type | Serial number | PMS SCS number
Docking and undocking | General & Docking | G01 | Vessel particulars | LOA: ___m BOA: ___m Depth:__m Est. Draft:__m The vessel is to be supported on keel blocks according to the applicable docking plan. Undue stress on the vessel's structure is to be avoided. Specific drawings for the vessel are attached. Shipyard to prepare and submit the Dock Black arrangement plan with clear block wise load distribution calculations, well in advance before arrival of the vessel in dock. Owner reserves the right to refuse docking of the vessel if the plan is not submitted in English as well as load distribution is not agreed. Laying of Dock Blocks to be inspected by attending Superintendent prior to docking of vessel. Average Height of Dock Blocks should be enough to inspect Hull and for carrying out blasting, painting and another repair works. Dock Block layout should clearly be marked to indicated UW appendages such as Echo Sounders, Speed Logs and similar. | [6 empty] | Approved | Major |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Agent | General & Docking | G02 |  | Owner will appoint a local agent for all coordination with local govt authorities on behalf of Owner and for towage, vessel movement/pilotage, administrative arrangement as well as boarding liaison. Contact details of the agent will be shared by Owner with shipyard accordingly. Owner will also appoint its own Ship’s Chandler for all necessary provision supplies and other miscellaneous requirements. Shipyard to provide access to the DD Agency as well as Owner's appointed Ship’s Chandler to the vessel and for performing their duties without obstruction. Shipyard to also ensure that no other ship’s chandlers, vendors or other unrecognised third-party service providers are making unsolicited calls to the attending Owner reps. | [6 empty] | Approved | Minor |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wharfage dues | General & Docking | G03 |  | If not free of charge please quote cost/day | [6 empty] | Approved | Minor |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Towage | General & Docking | G04 |  | The necessary services of boatmen, line handlers and/or deckhands, Tugs and Pilots will be required for manoeuvring the vessel. For tendering purposes you should assume the following vessel moves: • From sea in to the dry dock, and • From the dry dock to a suitable repair berth, and • Upon completion of repairs, from the repair berth to sea trial. Your tender should include all information and requirements for escort tug and Pilot assistance for the vessel from sea to and from the shipyard’s perimeter. All Tugs and Pilots etc. to and from the shipyards perimeter will be arranged through the vessels agents and will be a direct cost to owner. All other vessel moves with the shipyards tugs for the shipyards convenience will not be to the owners account. Including: • Linesmen / rigger • Pilots • Tugs | [6 empty] | Approved | Minor | 20/01/2022 | 26/01/2022 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0