## Sheet1
Title | Category | Dock list number | Supplier | Status | Priority | Start Date | Deadline | Description | Location | Specification | Gas free certificate | Light | Ventilation | Crane assistance | Cleaning before | Cleaning after | Work permit | Painting after completion | Parts on board | Transport to yard workshop | Transport outside yard | Material yards supply | Material owners supply | Risk assessment | Maker | Type | Serial number | PMS SCS number
Docking and undocking | General | G01 |  | Approved | Major |  |  | LOA: ___m BOA: ___m Depth:__m Est. Draft:__m The vessel is to be supported on keel blocks according to the applicable docking plan. Undue stress on the vessel's structure is to be avoided. Specific drawings for the vessel are attached. Shipyard to prepare and submit the Dock Black arrangement plan with clear block wise load distribution calculations, well in advance before arrival of the vessel in dock. Owner reserves the right to refuse docking of the vessel if the plan is not submitted in English as well as load distribution is not agreed. Laying of Dock Blocks to be inspected by attending Superintendent prior to docking of vessel. Average Height of Dock Blocks should be enough to inspect Hull and for carrying out blasting, painting and another repair works. Dock Block layout should clearly be marked to indicated UW appendages such as Echo Sounders, Speed Logs and similar. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Agent | General | G02 |  | Approved | Minor |  |  | Owner will appoint a local agent for all coordination with local govt authorities on behalf of Owner and for towage, vessel movement/pilotage, administrative arrangement as well as boarding liaison. Contact details of the agent will be shared by Owner with shipyard accordingly. Owner will also appoint its own Ship’s Chandler for all necessary provision supplies and other miscellaneous requirements. Shipyard to provide access to the DD Agency as well as Owner's appointed Ship’s Chandler to the vessel and for performing their duties without obstruction. Shipyard to also ensure that no other ship’s chandlers, vendors or other unrecognised third-party service providers are making unsolicited calls to the attending Owner reps. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wharfage dues | General | G03 |  | Approved | Minor |  |  | If not free of charge please quote cost/day |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Towage | General | G04 |  | Approved | Minor | 20/01/2022 | 26/01/2022 | The necessary services of boatmen, line handlers and/or deckhands, Tugs and Pilots will be required for manoeuvring the vessel. For tendering purposes you should assume the following vessel moves: • From sea in to the dry dock, and • From the dry dock to a suitable repair berth, and • Upon completion of repairs, from the repair berth to sea trial. Your tender should include all information and requirements for escort tug and Pilot assistance for the vessel from sea to and from the shipyard’s perimeter. All Tugs and Pilots etc. to and from the shipyards perimeter will be arranged through the vessels agents and will be a direct cost to owner. All other vessel moves with the shipyards tugs for the shipyards convenience will not be to the owners account. Including: • Linesmen / rigger • Pilots • Tugs |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Garbage removal | General | G05 |  | Approved | Minor | 20/01/2022 | 26/01/2022 | Garbage is to be collected and disposed of daily during vessel's stay at the yard. Yard to provide garbage containers placed on deck and in engine room. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gas free certificate | General | G06 |  | Approved | Minor | 20/01/2023 | 26/01/2023 | The services of a Marine Chemist are to be provided as required upon arrival of the vessel at the port of the shipyard. The vessel is to be tested and certified gas free and a certificate to this effect issued covering all tanks, cofferdams, bunker tanks, pump room and the engine room for access and/or repairs as required prior to docking and maintained throughout the repair period. Where works involving "hot work" are known, arrangements are to be made to have all affected spaces concerned tested for gas daily during repairs. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cooling water supply | General | G07 |  | Approved | Minor | 20/01/2024 | 26/01/2024 | Cooling water of sufficient pressure is to be supplied for the vessel's central cooling water system. Fresh water for chiller / provision plant as needed with adequate pressure to be supplied. Connection and disconnection of hoses are to be included in the tender. Separate cooling by seawater is to be arranged in case the fresh water system is drained off. Including: • Connection and disconnection: lines (Per Unit) • Colling Water Supply: line days (Per Unit) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fire water supply | General | G08 |  | Approved | Minor | 20/01/2025 | 26/01/2025 | A supply of water with a minimum pressure of 10 kg/cm2 is to be connected to the ship's fire line for the duration of the vessel's stay for the Fire Fighting Services. Any additional fire/safety services or requirements are to be specified and quoted for if Yard or local regulations demand. Including: • Fire water supply (Qty:__ lines) • Connection and disconnection of fire water lines |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ballast water supply | General | G09 |  | Approved | Minor | 20/01/2026 | 26/01/2026 | Supply of clean, treated ballast water compliant with the IMO Ballast Water Management (BWM) standards. The source of the ballast water must free from contaminants and invasive species. Including: • Ballast water supply (____ tons) • Connection and disconnection of BW lines |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Potable water supply | General | G10 |  | Approved | Minor | 20/01/2027 | 26/01/2027 | Supply potable water that meets or exceeds WHO drinking water standards or any other applicable national standards. Ensure it's from a safe and approved source, free from contaminants, pathogens, and any other harmful substances. Utilize dedicated potable water supply lines distinct from other lines to prevent cross-contamination. These lines must be sanitized, flushed, and cleaned prior to the transfer. Including: • Portable water supply (____ tons) • Connection and disconnection of portable water lines |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Compressed air supply | General | G11 |  | Approved | Minor | 20/01/2028 | 26/01/2028 | Vessel’s service air system to be connected to the Yard’s service air system (7-8 bar). Including: • Compressed air supply for __days • Connection and disconnection of air supply |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Crane service | General | G12 |  | Approved | Minor | 20/01/2029 | 26/01/2029 | Crane service and other transportation services for provisions, machinery parts and other stores to be provided as requested. Yard to inform minimum notice required. Including: • Crane assistance incl. signal man (__ hours) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Heating lamps | General | G13 |  | Approved | Minor | 20/01/2030 | 26/01/2030 | Heating lamps are to be provided as required by the attending owner’s representative. Including: • Heating lamps (Qty:__/__days) • Connection and disconnection of heating lamps |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Telephone and internet | General | G14 |  | Approved | Minor | 20/01/2031 | 26/01/2031 | Superintendent’s office is to be equipped with telephone and high-speed internet connection at no extra cost. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Power supply | General | G15 |  | Approved | Minor | 20/01/2032 | 26/01/2032 | An electrical power supply of <number_of_phases>x<power_voltage>V <AC_or_DC> at <power_frequency> Hz is to be connected to the vessel as soon as deemed necessary by the Owner’s representative. Yard should be able to supply a minimum of <minimum_amp_required>amps continuously under these conditions. Including: • Power supply (____kWh) • Connection and disconnection of power supply |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sewage disposal | General | G16 |  | Approved | Minor | 20/01/2033 | 26/01/2033 | During the period the vessel is in dry dock, the yard is to install a sanitary line for connection to vessel's soil overboard pipe and led to suitable sewage collection tank. Certificates to be provided on completion as to quantity of sewage removed from vessel and disposal ashore in approved facilities. Including: • Disposal of sewage, incl. holding tanks • Disposal of sewage water • Connection and disconnection of sewage line • Additional costs for environmental documents • Rental of tanks (day rate) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ventilation | General | G17 |  | Approved | Minor | 20/01/2034 | 26/01/2034 | Ventilation fans and lights to be supplied by the Yard as required and to be included in quotes or specified if not included. Including: • Ventilation usage • Connection and disconnection per fan |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scuppers | General | G18 |  | Approved | Minor | 20/01/2035 | 26/01/2035 | The vessels overboard discharges are to be fitted with extension pipes and/or hoses to direct discharges away from the vessels hull. The method adopted by the shipyard in providing suitable extension pipes is to the shipyards own practise however the method adopted must be sufficiently tight to prevent water running down the ships side. Including: • Extension of air conditioning overboard • Extension of domestic refrigeration plant overboard • Extension of sewage tank overboard • Extension of gally scupper and drain discharge • Extension of deck scuppers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cleaning | General | G19 |  | Approved | Minor | 20/01/2036 | 26/01/2036 | Every endeavour is to be made to remove debris and dirt at regular intervals throughout the repair period and the vessel is to be thoroughly cleaned of all dirt and debris on completion of repairs and these costs are to be inclusive in with your Tender. Particular attention to engine room, cargo room, accommodation, bridge and tanks and weather deck high pressure washing with soap. Yard to quote cost for: a) Wash down of complete vessel from radar mast to main and poop deck. b) Wash down and cleaning of engine room bilges. c) Wipe down of accommodation floors and bulkheads. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hull thickness measurements | Hull | H01 |  | Approved | Minor | 20/01/2037 | 26/01/2037 | Ultrasonic thickness measurements to be undertaken as directed by the attending Classification Society Surveyor. Including: • UTM spots: ___ |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hull treatment and preparation | Hull | H02 |  | Approved | Minor | 20/01/2038 | 26/01/2038 | Top sides: <area_top_sides>m^2 Bottom sides: <area_bottom_sides>m^2 Flat bottom: <area_flat_bottom>m^2 The following is for information only. • Yard to ensure that all items such as consumables, use of cherry pickers, dock arms, craneage, staging, lighting ventilation are to be included in quotes. All paint for use on the vessel will be owners supply unless otherwise stated. The paint brand will be advised after appointment of the shipyard. • Adequate access is to be provided for Owner’s and Paint Suppliers representative is to be provided for all areas involved. • Following the treatment and the preparation of the hull surfaces to be coated, no paint is to be applied until those surfaces are verified clean, dry and have been inspected and approved by the attending Owner’s Representative. • Yard to provide protection for life rafts, lifeboats, embarkation ladders, handrails, deck equipment and personnel from grit blasting, by use of plywood sheeting and from overspray by similar or plastic sheeting. Any overspraying is to be corrected. • Masking of hull fittings such as ICCP anodes, echo sounders, speed logs etc. to be included. • All work will be supervised by the attending Owner’s Representative or person nominated by them. • The blasting grit shall be un-recycled copper slag unless otherwise stated. Ensure all costs incurred for mobile cranes, staging for access, etc. are included in the rates, also any additional costs not requested but are likely to be incurred should be identified and clearly stated in the quote. • Yard to also ensure cleaning of Grit on entire vessel after blasting and in dock is done to the satisfaction of attending Suptd/Paint specialist. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hull painting | Hull | H03 |  | Approved | Minor | 20/01/2039 | 26/01/2039 | Top sides: <area_top_sides>m^2 Bottom sides: <area_bottom_sides>m^2 Flat bottom: <area_flat_bottom>m^2 • The Vessel's hull is to be treated in accordance with the paint specifications from paint maker and as per Owner appointed Coating Advisor / Paint Specialist • Shipyard to ensure distance of at least 3 meters is maintained between the dock wall and vessel hull at maximum breath to provide free access to inspection and movement of cherry pickers /spray painting • Shipyard to also inform Owner during the tender or at the earliest possible but prior to entry of vessel in dock, about its intention to use any alternate type of surface preparation method for paint application than what has been specified in the paint specifications • Owner will reserve the right to agree on extra costs/extra days basis valid justification in case of such a change • Owner will appoint a paint specialist / Coating advisor and shipyard to ensure free access but not limited to vessel inside dry-dock, painting areas including store & workshops and surface preparation booths for necessary inspections • The unit prices should include any kind of access work and equipment such as possible staging, dock arm rental and cherry pickers etc. • Meeting between yard, paint supplier and owner to be held prior to work start in order to agree on correct work procedure • Painting must not be carried out at night or in darkness unless approved by Owner's representative. If painting approved to be carried out at night or in darkness, the yard must supply sufficient lighting to ensure quality of work to be maintained • Owner or paint supplier have the right to stop ongoing paint job if the quality of the work done isn't meeting expected standard, this will be on the yards account and responsibility • Roughness of hull is to be measured after hose down before first coat, and on completion of paint application. Measurement to be taken by paint suppliers’ representative • First coat of paint to be applied before rusting of the cleaned surface occurs • All paint to be applied by airless injection with correct type of nozzle and cross spray technique shall be used to obtain the specified film thickness • Paint to be applied only on dry surfaces, free from dust, salt, fouling, loose paint, residues and other impurities • The use of clean pumps and new paint hoses including spray lines and tips is to be included in the tender • The number of coats, the dry film thickness and the manner and sequence in which they are applied needs to be in accordance with the specification • Thinning of paints to be kept to a minimum and may only take place if approved by owner's representative • To ensure a good result, the specified re-coat intervals adjusted to ambient temperature must closely be adhered to • To ensure a good result the paint foreman must be aware of this specification. Foreman needs to be English speaking • Disposal of empty paint tins shall be included in the tender • Vessel to be fully cleaned and all garbage/sludge/rags/fire hazards to be cleared prior departure of vessel from yard. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hull markings | Hull | H04 |  | Approved | Minor | 20/01/2040 | 26/01/2040 | The vessel’s distinguishing marks are to be painted in with two coats of Owner’s supply paint once the underlying coatings are dry. Your quotation should include all necessary staging or other means of access. Surface preparation is considered unnecessary as the marks will be painted onto newly applied hull coatings. Cutting in of lines to be included. Yard to quote for: 1. The vessel’s Name forward in 2 locations 2. The vessel’s Name and Port of Registry aft in 1 location 3. Owners “Flag“ markings in 2 locations 4. The vessel’s Draught Marks in a total of 6 locations 5. The vessel’s Load Line and Plimsoll Marks in 2 locations 6. The vessel’s Tug Marks in 4 locations 7. Pilot ladder markings painted in 2 locations with the appropriate colors supplied. 8. The vessel’s full set of Manifold Marks both port and starboard 9. The Vessels IMO number on the aft transom in one location 10. Sea grids positions, echo sounder and speed logs etc. 11. White band between boot top and top side, 350 mm high around entire ship 12. Installation or painting of corporate logos Quoted costs to include Cherry picker, mobile and stationary crane usage, staging or other means of access where necessary is to be allowed for and included in the quotation. Yard to include costs for removal and disposal of used paint tins. Owner will supply all the required paint and thinners. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chain lockers | Hull | H05 |  | Approved | Minor | 20/01/2041 | 26/01/2041 | Number of chain lockers : 2 Number of access points: 2 per locker Work scope: 1. Removal and subsequent refitting of at least two accesses covers where possible for each chain locker 2. Removal of mud and sludge from bottom of chain locker followed by HP water wash of the internal area, for inspection 3. Staging out of each chain locker to the top based on the dimensions given in the above table 4. Preparation of any bare steel areas to St3, application of 2 x 150mic DFT coats of Owner’s supply paint. Advise any minimum area requirement if applicable 5. Proving clear of bilge lines after completion of the above work. Allow for the provision of lighting, ventilation and safe means of access into the chain locker to inspect the lower part of the chain locker prior to staging. Including: • Removal of mud and HP wash per locker • Staging • Preparation of nay bare steel • Providing clear of bilge lines |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sea chests & Grids | Hull | H06 |  | Approved | Minor | 20/01/2042 | 26/01/2042 | Sea chests to be carefully cleaned and painted according to the specification. Anodes are to be replaced with spares supplied by the vessel. On completion of all work, gratings to be refitted and secured with stainless steel fittings to the satisfaction of the Owner's representative. Any substitute to be of similar grade as the original material. After grit blasting, first coat of paint to be applied before rust occurs. If grit blasted surfaces are severely rusted due to water condensation, rain or similar, re-grit blasting or grit sweeping to be executed. Including: • Removal of protective grid • Replacement of grids • Staging • Thorough cleaning • HP washing • Blasting to SA 2.0 • Fresh water flushing • Application of coating – 1x170mic DFT FC of antifouling to entire chest |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bottom plugs | Hull | H07 |  | Approved | Minor | 20/01/2043 | 26/01/2043 | All bottom plugs are to be removed as soon as the dock is dry in order to empty the tanks prior to blasting and painting. Vessel's Chief Officer to collect and supervise opening of all tank bottom plugs. When bottom plugs have been fitted again tightness to be verified by vacuum testing with vessel's Chief Officer or a person nominated by Owner's representative. Plugs are to be fitted back with washers of approved type. Quote to include any access work. Including: • Removal & refitting • Vacuum test • Sealing cement • Vacuum testing on completion of repair • Touch up of coating both internally and externally • Cropping and renewing of bottom plug |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hull anodes | Hull | H08 |  | Approved | Minor | 20/01/2044 | 26/01/2044 | Various sacrificial anodes require replacement in hull and rudder as per drawings. The existing anodes are welded in place. Including: • Cherry pickers • Staging • Yard supply AL anode material • Yard supply zinc anode material • Removal & disposal of old anodes • Cleaning up and making good the existing hull attachment arrangements • Fitting of new anodes • Protection of new anodes • Preparing damaged coatings |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sea chest anodes | Hull | H09 |  | Approved | Minor | 20/01/2045 | 26/01/2045 | The following work is to be done in conjunction with work order 206 - Sea Chests & Grids and as such the same means of access is to be used. Work scope includes: 1. Removal and disposal of the spent anodes from their attachments as directed by the owner’s representative. 2. Cleaning up and repairing the existing sea chest attachment arrangements. 3. Fitting the new owners supplied anodes. 4. Protecting the anodes during their exposure in the dry-dock from overspray. Any temporary protection is to be removed before the anodes become immersed. Disturbed or damaged coatings must be repaired to the same specification as the surrounding area. On completion of painting and before closing up of any sea grids the owner’s representative is to witness the removal of the protective coatings. Including: • Removal and disposal of the spent anodes • Cleaning and repairing existing sea chest attachment and arrangements • Fitting the new anodes • Protecting the anodes during their exposure in the dry-dock from overspray • Staging |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGPS Anodes | Hull | H10 |  | Approved | Minor | 20/01/2046 | 26/01/2046 | This work is to be carried out in conjunction with work order - Sea Chest & Grids. A manufacturer’s service technician will be arranged by the Owner’s representative to attend the vessel to service and provide necessary maintenance of the MGPS system. The required spares will be of Owners supply. The Yard is requested to provide all necessary assistance in allowing the owners appointed representative(s) safe and free access to the vessel in pursuit of their contractual obligations. Including: • Yard fitter • Staging • Cherry picker |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ICCP | Hull | H11 |  | Approved | Minor | 20/01/2047 | 26/01/2047 | A manufacturer’s service technician will be arranged by the Owner’s representative to attend the vessel to service and provide necessary maintenance to the ICCP system. The Yard is requested to provide all necessary assistance in allowing the owners appointed representative(s) safe and free access to the vessel. 1. Upon arrival to the ship yard prior to docking, 2. Whilst positioned on the blocks, and 3. After immersing the dry docking Including: • Yard electrician • Cherry picker • Staging • Blasing around anodes • Applying new epoxy resin • Protection |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chain locker survey | Ship equipment | SE01 |  | Approved | Minor | 20/01/2048 | 26/01/2048 | Yard to quote cost for: 1. Removal and subsequent refitting of at least two accesses covers where possible for each chain locker. 2. Removal of mud and sludge from bottom of chain locker followed by HP water wash of the internal area, for inspection. 3. Staging out of each chain locker to the top based on the dimensions given in the above table. 4. Preparation of any bare steel areas to St3, application of 2*150mic DFT coats of Owner’s supply paint. Advise any minimum area requirement if applicable. 5. Proving clear of bilge lines after completion of the above work. Allow for the provision of lighting, ventilation and safe means of access into the chain locker other than where specified in (3) above to inspect the lower part of the chain locker prior to staging. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Anchor chains | Ship equipment | SE02 |  | Approved | Minor | 20/01/2049 | 26/01/2049 | Number of anchors: <number_of_anchors> Anchor maker: <anchor_maker> Anchor type: < anchor_type> Anchor diameter: <anchor_diameter> Anchor weight: <anchor_weight> Anchor material grade: <anchor_material_grade> Scope of work: 1. Ranging of all anchors and chains neatly into the drydock bottom. 2. High pressure water washing of all anchors and ranged chains. 3. Blasting of anchors in way of joining shackle, swivel, lower end of stock to enable inspection of pin. 4. Recording clearance of swivel, joining shackle and stock lower pin. 5. Checking and recording of all defects found with anchor and chain pins, shackles, swivels, Kenter links etc. 6. Calibrate representative links in all shots and Kenter links to the owners and surveyors requirements. All measurements are to be recorded and submitted to owners representative and the class surveyor. 7. Disconnecting of the outer two shots of cable and connecting anchor to new outer end of cable. 8. Disconnecting the cable at the bitter end and inserting the removed two shots. 9. Replacement of lead plugs in Kenter shackles. 10. Welding one end of loose studs in cable links. 11. Painting of each anchor with two coats of owners supplied paint. 12. Painting and marking of Kenter shackles and links with owners supplied paint and as per standard practice Fitting of shipyard supplied stainless steel banding, 2 per shot as required. Including: • Range all anchors into dock bottom • HP washing of all anchors & chains • Recording clearance of swivel, joining shackle and stock lower pin • Blasting of anchor, shackle & swivel • Checking & recording of all defects • Calibration of representative links • Disconnection of outer two shorts & connection of anchor to new outer end of cable • Disconnection of bitter end & insertion of removed shots • Replacement of lead plugs each • Welding of one end of loose stud • Painting anchors • Painting and marking of Kenter shackles and links with owners supplied paint and as per standard practice Fitting of shipyard supplied stainless steel banding |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mooring winch and Windlass | Ship equipment | SE03 |  | Approved | Minor | 20/01/2050 | 26/01/2050 | Windlass maker: <windlass_maker> Windlass type: <windlass_type> Number of windlasses: <number_of_windlasses> Scope of work: 1. Hydraulic inlet/outlet lines to the motors to be isolated, blanked, lockout/tagout procedure to be followed. 2. Hydraulic motor to be dismounted. 3. Yard to supply the correct rigging, scaffolding, chain blocks and wire slings to allow for motor removal for overhaul. 4. The motors have to be dismounted and transported to a suitable clean workshop for overhauling. 5. The noise emanating between the hydraulic motor drive gear and the spur gear wheel to be investigated and rectified. 6. Hydraulic motor must be thoroughly inspected for condition. Special attention is to be paid to small/large displacement piston including related parts and front and rear roller bearings. 7. Following inspection worn spares are to be replaced with new. 8. Hydraulic motors to be re-assembled using new seals and transported back to vessel forecastle. 9. Hydraulic motor to be re-installed on windlass, gear box filled with oil, system de-isolated and vented in accordance with the Manufacturer’s instructions. 10. The windlass is to be tested in operation and good working condition to be confirmed. 11. The hydraulic control unit to be overhauled and condition of logic working element checked. 12. Service engineer will be in attendance to oversee maintenance. 13. Qualifies riggers and fitters to work under the supervision of the attending Service Engineer. All tools and lifting equipment is to be of yard supply including crane. O-rings, seals, bearings and gaskets will be of vessel/service engineer supply. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rudder | Ship equipment | SE04 |  | Approved | Minor | 20/01/2051 | 26/01/2051 | Number of rudders: <number_of_rudders> Rudder maker: <rudder_maker> Rudder type: <rudder_type> Rudder weight: <rudder_weight> Rudder area: <rudder_area> Scope of work: Rudder bearing clearance 1. Removal and replacement of all bearing access plugs and plates. 2. Measurement and recording of all rudder bearing pintle clearances, rudder wear down and jumper clearance. 3. Presentation of the above results to the owner’s representative at earliest opportunity. Allow for staging to a height of 10M. All quotations to include the necessary provision of lighting and ventilation. Rudder plugs. 1. Removal and replacement of all rudder bottom plugs to check for issuance of water. The removal of the plugs is to be witnessed by the Owners Representative and attending classification society surveyor. 2. In the event of water issuing from the rudder plugs when removed, quote for pressure testing of the rudder to 0.25 bar with compressed air or an alternative pressure as directed and testing of all welded seems with a soapy water solution. 3. Rudder to be filled with a solution of fresh water and anti-corrosion additive and then drained to leave an additive coating on the internal surfaces. Allow for staging or alternate means of access to a height of 10M for access. Rudder removal 1. Measuring and recording for submission to owners and class all rudder pintle bearing and rudder wear down clearances as per above work. 2. Cropping out and subsequent re-welding of rudder nut access plates. Welds to be NDT tested on completion. 3. Removal and subsequent refitting of rudder nut. 4. Renewal of seals in hydraulic nut, seals are Owner’s supply. 5. Removal and subsequent refitting of rudder. Provision of safe storage for the removed rudder on suitable supports. Should this work overrun with the hull coatings then provision should be allowed for coating the rudder according to the specifications detailed by the coating suppliers. 6. Taking of another set of rudder pintle bearing and rudder wear down clearances for submission to owners and class. Allow staging to a height of 15M above the keel in 2 locations. Allow for fabrication and fitting of temporary padeyes, welds to be NDT tested. On completion of work, padeyes to be removed and any damaged coating to be prepared and coated as per hull coating specification. Including: • Staging • Removal & refitting of rudder • Fitting and removal of pad eyes • Renewal of hydraulic nut seals • Cropping & re-welding of rudder nut access plates • Anti-corrosive flushing • Vacuum test • Pressure testing of rudder • Removal and replacement of plugs • Measurement and recording of all rudder bearing pintle clearances, rudder wear down and jumper clearance and present results to owner's rep. • Removal & replacement of all access plugs & plates |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Steering gear service | Ship equipment | SE05 |  | Approved | Minor | 20/01/2052 | 26/01/2052 | The Owner will appoint a service contractor to complete the 5 year service of the vessels Steering Gear and Associated Systems. The yard is requested to allow the Owner appointed sub-contractor free and unhindered access to and from the vessel in execution of their contractual obligations. Spare parts required for the service will be of owners supply. Yard to quote for two mechanical fitters to assist the owners appointed service engineer. Including: • Assistance to Service Engineer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Side thrusters | Ship equipment | SE06 |  | Approved | Minor | 20/01/2053 | 26/01/2053 | Number of bow thrusters: <number_of_thrusters> Maker, bow thruster: <bow_thruster_maker> Type, bow thruster: <bow_thruster_type> Power, bow thruster: <bow_thruster_power> Number of stern thrusters: <number_of_thrusters> Maker, stern thruster: <stern_thruster_maker> Type, stern thruster: <stern_thruster_type> Power, stern thruster: <stern_thruster_power> Scope of work: 1. Replace drive shaft seals. 2. Side thrusters tunnel to be cleaned and all shell etc. to be removed. 3. Propeller blades to be checked for cracks and damages. Damaged blades to be rectified according to makers instructions and approval. 4. Pittings inside thruster tunnels to be re-welded. 5. Pittings on propeller shaft to be rectified according to makers instructions and approval. 6. The thrusters tunnel to be coated with paints according to supplier’s instruction Including: • Cleaning • Grinding & Welding • Withdrawal of parts • Coating |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tailshaft weardown | Ship equipment | SE07 |  | Approved | Minor | 20/01/2054 | 26/01/2054 | Scope of work: 1. Measuring and recording of the tail shaft wear down readings using the vessels supplied poker gauge. Readings to be witnessed by Owners representative. 2. Copy of readings to be submitted to Owner’s representative and to the Class Surveyor as soon as possible. Including: • Staging • Measuring wear down • Submission of report to owner |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tailshaft removal for survey | Ship equipment | SE08 |  | Approved | Minor | 20/01/2055 | 26/01/2055 | The following work to be carried out in conjunction with the following work orders: • Stern Seal Replacement • Rudder Scope of work: 1. Measuring and recording the bearing loads at the forward stern tube bearing, the intermediate shaft bearing(s) and gear train or main engine flywheel using the shaft jack up method. The readings are to be taken with the vessel securely on the blocks within the drydock and the propeller attached. The measurements are to be repeated after completion of all propeller shaft works and under the same conditions as the initial readings were established. Any significant deviations between before and after readings will require corrective action. 2. Disconnecting and removing to a safe location all instruments and power meters and their guards as detailed above. Reconnecting upon completion of all works. 3. Release of both couplings of the adjacent intermediate shaft and provision of suitable lifting gear to lift the intermediate shaft. 4. Opening up the intermediate shaft bearing(s) and lifting clear the intermediate shaft to a location which allows for safe storage whilst the tail shaft is being drawn inboard. Allowance should be made in your quotation for complete removal of the intermediate shaft bearing(s) to facilitate tail shaft withdrawal. 5. Withdrawing the tail shaft inboard sufficiently to allow for survey of the stern bearings. It is not foreseen at this time that the tail shaft requires to be removed from within the vessel. 6. Cleaning of all bearing surfaces, tail shaft and intermediate shaft running surfaces. These areas are to be protected during exposure. 7. Reassemble the tail shaft back into the stern bearing. 8. Reassembling all intermediate shaft bearings back into position using the same shims. Reassembling the intermediate shaft and reconnect the shaft couplings to the same coupling fit criteria and tolerance as defined by the manufacturers. Important notes 1. No movement of the tail shaft in or out of the stern tube bearing is to take place without the owner’s nominated representative being present. 2. All procedures, torques or ‘fit’ criteria for the shaft couplings are to be according to the manufacturer’s criteria as defined within the approved drawings. These drawings will be supplied by the owners to the shipyard. 3. All bearing jack up loads are to replicate as far as is reasonable, those taken initially before removal of the tail shaft but in no way exceed the tolerances as defined within the approved drawings. These drawings will be supplied by the owners to the shipyard. Your tender shall include all necessary staging for access, lighting, ventilation and the supply, fitting and removal of any additional temporary brackets as required making good the any disturbed structure after bracket removal. Including: • Measuring of bearing loads • Disconnection & reconnection of all meters • Release of couplings • Opening of shaft bearing & lift clear inter shaft • Withdrawal of tail shaft • Cleaning of running surfaces • Refitting of tail shaft • Refitting of inter shaft & closing of shaft bearing • Refit / remove floor plates |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Propeller polish | Ship equipment | SE09 |  | Approved | Minor | 20/01/2056 | 26/01/2056 | Number of propellers: <number_of_propellers> Propellers, maker: <propeller_maker> Propellers, type: <propeller_type> Propellers, number of blades: <number_of_blades> Propellers, diameter: <propeller_diameter> Propellers, pitch: <propeller_pitch> Propellers, material: <propeller_material> Propellers, weight: <propeller_weight> The propeller(s) are to be polished to 1 C.L.A. (Centre Line Average) standards. Scope of work: 1. Grinding each tip in way of slight damage on both the leading and trailing edges of each blade to achieve the blades original profile. Details of damage recorded at In Water Survey can be found below. Allow for production of a template to ensure all blades have an identical profile. Profiling of propeller blades is to be completed following consultation with the attending class surveyor and the Owners representative 2. Dye checking of the blade roots and both sides of all blade edges. Polishing the propellers in drydock to 1 C.L.A (Centre Line Average) standards 3. Coating the propellers with fish oil, soft soap or equivalent protective material Allow staging to a height of 5M. Including: • Grinding of tips and repair of damaged tips • Dye pen of roots & tips • Polishing • Coating with fish oil or soap • Staging |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Propeller removal | Ship equipment | SE10 |  | Approved | Minor | 20/01/2057 | 26/01/2057 | Number of propellers: <number_of_propellers> Propellers, maker: <propeller_maker> Propellers, type: <propeller_type> Propellers, number of blades: <number_of_blades> Propellers, diameter: <propeller_diameter> Propellers, pitch: <propeller_pitch> Propellers, material: <propeller_material> Propellers, weight: <propeller_weight> The propeller(s) are to be polished to 1 C.L.A. (Centre Line Average) standards. Scope of work: 1. Recording all necessary propeller position measurements in relation to the shaft prior to removal. 2. Removal and replacement of the propeller boss cap, propeller nut and propeller using shipyard supplied hydraulic equipment and lifting gear. Note the propeller is to be refitted using owners supplied grease. The propeller is to be hung clear of the tail shaft in a safe location. 3. NDT checking of taper in way of propeller fitting surface and lower area of threaded section. 4. Transportation to and from a suitable propeller cleaning and storage area ashore. Include quotation for staging towers at two locations. Allow for fitting of lifting bracket to assist. Including: • Recording of positions • Removal & refitting of boss cap, nut & prop • NDT of taper • Transport shore • Staging |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stern seal replacement | Ship equipment | SE11 |  | Approved | Minor | 20/01/2058 | 26/01/2058 | Please advise whether a Manufacturers Trained Technician is present in the yard, in which case they will be employed. Otherwise, a manufacturer’s service engineer will be appointed by the Owner to supervise the work and provide assistance. Before any work is commenced on the seal, it should be confirmed that ship staff have drained the system. Scope of work: 1. After Seal a. Removal and replacement of the rope guards and or net cutters for access to the aft stern seals. b. Fabrication of new rope guards. c. Dismantling of the aft seal assembly, cleaning for inspection. Reassembly of seal with Owner’s supply new seals. Seals will be cut and bonded in situ by service engineer. d. Quote separately for removal of stern seal liner and transporting to and from shore workshop for light machining to remove wear grooves. N.B. Cost for removal of propeller is covered in Job “Propeller removal”. 2. Fwd Seal a. Dismantling to forward seal assembly, cleaning for inspection. Reassembly using owner’s supply seals. Seals will be cut and bonded in situ by service engineer. No staging required. Upon completion of all works, allow 24 hrs for leak testing of the forward and aft seals using static pressure from the ships own lubricating oil system. Quote should allow for the provision of all necessary lighting, ventilation, additional temporary lifting brackets and transportation. Including: • Removal & replacement of rope guards • Dismantling, cleaning & reassembly of seal assembly • Removal of liner to workshop for machining • Staging • Drain seal oil, refill & leak test |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engine Room Crane Load Test | Ship equipment | SE12 |  | Approved | Minor | 20/01/2059 | 26/01/2059 | In compliance with ILO Convention it is a requirement to load test the Lifting Appliances. In accordance with the above stated ILO Conventions and Recommendations, the test loads shall be assumed to follow the generic pattern as follows: SWL: Up to 20 tons Test load: 25% in excess SWL: 20 to 50 tons Test load: 5 tons in excess SWL: 50 tons and above Test load: 10% in excess In the case of hydraulic cranes where pressure limitations may render the crane incapable of achieving 125% loads, then a load test can be performed that should generally achieve not less than 110% load. Scope of work: • Carrying out a load test on the Engine Room crane. • Allow for provision of necessary weights or water bags. • Allow for provision of load cell. • Owners representative and Class Surveyor to be present during test. • On completion of work a certificate should be issued to Owner’s representative an attending Class Surveyor. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lifeboat 5 Year Service | Equipment for crew and passengers | EC01 |  | Approved | Minor | 20/01/2060 | 26/01/2060 | There is a requirement for the lifeboat to be landed for 5 year service by a maker’s authorised service company. Scope of work: 1. Removal and subsequent refitting of the lifeboat from its position onboard and lowering to the quayside. 2. Transporting to and from shore workshop. 3. Weighing of lifeboat to ascertain correct load test weight using a strain gauge and a certificate provided. 4. Yard to HP wash lifeboat following maintenance and coat with 2 coats of owners supplied orange paint. 5. After completion of work by Owner’s service contractors, lifeboat to be lowered and subsequently recovered from the water near the drydock to allow testing and trials Trials to be witnessed by attending Class Surveyor. Notes: • Allow for construction of support cradle to secure the lifeboat in an upright position to allow maintenance to be carried out. • Allow for all transportation, rigging, cranage and personnel for lifeboat in-water trials. • Allow for test certificate to be issued within final yard quality assurance certificates. Including: • Removed ashore and refitted • Weighting of lifeboat + load test + class certificate • Transportation to and from workshop • HP washing & Painting • Testing and trials |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lifeboat Davit Service | Equipment for crew and passengers | EC02 |  | Approved | Minor | 20/01/2061 | 26/01/2061 | Carry out a 5 year service of the lifeboat davit. Scope of work: 1. Port and starboard life boat davits to be dynamically load-tested and verified by Class surveyor 2. After load test and before boats are lifted back in place release gear of both life boats to be tested and verified by Class surveyor 3. Certificate of Load and release test is to be issued and handed over to vessels management before departure, copy to be handed over to Superintendent in charge 4. Release gear of both life boats to be overhauled by an approved workshop and verified by Class surveyor. Yard to quote if authorized to provide such service for 5 yearly service of the boats & davits 5. Change of lifeboat davits wire Including: • Lifeboat Davit – Dynamic load test according to SOLAS regulations • Changing lifeboat davit wire • Issue class approved certificate |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lifeboat Air Cylinder Pressure Testing | Equipment for crew and passengers | EC03 |  | Approved | Minor | 20/01/2062 | 26/01/2062 | The following work should be carried out when the boats have been lifted from their davits and secured on the quayside. Scope of work: 1. Disconnection, draining, removal and subsequent refitting of all air bottles from the boat. 2. Landing and transportation of the bottles to and from the vessel to shore facilities capable of hydraulically testing each bottle under safe and controlled conditions. 3. Hydraulically testing each bottle to its test pressure and issuing appropriate test certificates. The bottles are to be recharged to their nominal working pressure with air of breathable quality. Allow for removing panels and seats for access as shown in attached drawing. Including: • Lifeboat Air Cylinder Pressure Testing (Qty: __) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rescue Boat 5-year Service | Equipment for crew and passengers | EC04 |  | Approved | Minor | 20/01/2063 | 26/01/2063 | There is a requirement for the rescue to be landed for 5 year service by a maker’s authorised service company. Scope of work: 1. Removal and subsequent refitting of the rescue boat from its position onboard and lowering to the quayside. 2. Transporting to and from shore workshop. 3. Weighing of rescue boat to ascertain correct load test weight using a strain gauge and a certificate provided. 4. Yard to HP wash rescue boat following maintenance and coat with 2 coats of owners supplied orange paint. 5. After completion of work by Owner’s service contractors, rescue boat to be lowered and subsequently recovered from the water near the drydock to allow testing and trials. Trials to be witnessed by attending Class Surveyor. Notes: • Allow for construction of support cradle to secure the rescue boat in an upright position to allow maintenance to be carried out. • Allow for all transportation, rigging, cranage and personnel for rescue boat in-water trials. • Allow for test certificate to be issued within final yard quality assurance certificates. Including: • Removed ashore and refitted • Weighing of rescue boat + load test + class certificate • Transportation to and from workshop • HP washing & Painting • Testing and trials |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fast Rescue Boat Davit Service | Equipment for crew and passengers | EC05 |  | Approved | Minor | 20/01/2064 | 26/01/2064 | Scope of work: 1. Load test to be carried out. Emergency operation to be tested. Test to be witnessed by Class surveyor in conjunction with attending superintendent or Chief Engineer. 2. Certificate of load test is to be issued and handed over to vessels management before departure. One copy is to be handed over to Superintendent in charge. 3. Change of rescue boat davits wire. 4. Rescue Boats to be functionally tested in Calm waters prior sail out of vessel or just after sailing out from yard but before loading cargo at first port and in attendance of specialist/service engineer. Including: • Lifeboat David – Dynamic load test according to SOLAD regulations • Changing lifeboat davit wire • Issue class approved certificate |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Accommodation Ladder Load Test | Equipment for crew and passengers | EC06 |  | Approved | Minor | 20/01/2065 | 26/01/2065 | Scope of work: 1. Removal and subsequent refitting of the two accommodation ladders from vessel including transport to/from quay Thorough inspection of entire length of each ladder. Report to be presented to owners representative. 2. Load test to 110% of SWL of all four ladders using sandbags or similar evenly spread across the ladder, ladder to be supported at ends with trestles. Load test to be witnessed by Owners representative. 3. Display Plaques (Laser cut) to be made up for each accommodation ladder. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Provisions Crane Load Test | Equipment for crew and passengers | EC07 |  | Approved | Minor | 20/01/2066 | 26/01/2066 | In compliance with ILO Convention it is a requirement to load test the Lifting Appliances. In accordance with the above stated ILO Conventions and Recommendations, the test loads shall be assumed to follow the generic pattern as follows: SWL: Up to 20 tons Test load: 25% in excess SWL: 20 to 50 tons Test load: 5 tons in excess SWL: 50 tons and above Test load: 10% in excess Scope of work: 1. Carrying out a load test on the Provisions Gantry Crane. 2. Load test to be witnessed by Owners Representative and attending Class Surveyor. 3. Allow for provision of necessary weights or water bags. 4. Allow for provision of load cell. 5. A certificate to be provided upon completion of work |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fixed Firefighting CO2 System Bottles | Equipment for crew and passengers | EC08 |  | Approved | Minor | 20/01/2067 | 26/01/2067 | A complete service of the fixed CO2 system. All of the CO2 bottles to be taken ashore for hydrostatic pressure testing. Include cranage in quote id necessary. Provide certificate of completed work. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ME Turbochargers | Machinery main components | MM01 |  | Approved | Minor | 20/01/2068 | 26/01/2068 | Turbocharger Maker: Turbocharger Type: Turbochargers for main engine to be fully overhauled. Rotors to be inspected, calibrated, balanced, bearings, nozzle ring exchanged as necessary. There may be a requirement to carry out the overhauls in a shore workshop, if so, all necessary costs are to be included, such as craneage and transportation to and from workshop. Including: • Craneage to remove and return Turbochargers from engine room to dockside • Transportation to and from shore workshop • Standard overhauling • Dynamic balance test • Extract and refit nozzle ring • Sandblasting of nozzle rind or turbine blade (if necessary) • Dye check Nozzle ring / Turbine Blades |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ME Fuel injection pumps | Machinery main components | MM02 |  | Approved | Minor | 20/01/2069 | 26/01/2069 | Scope of work: • Perform a complete overhaul of all Fuel Oil (FO) pumps for the main engine. • Calibrate and re-pack the FO pumps as required. • Replace any worn plunger and barrel components with new spares from onboard stock, as necessary. • Conduct a thorough inspection of the fuel pump roller guide. • Verify the condition and operation of the puncture valve. • Assess and confirm the injection timing of the main engine is within specified parameters. Special Instructions: • The vessel owner is responsible for coordinating with the engine manufacturer's representative to oversee the overhaul process. • The Variable Injection Timing (VIT) system requires adjustment. This should be carried out by the manufacturer's representative during the vessel's sea trial to ensure optimal engine performance Including: • Removing the fuel pumps from the engine and transport to/from workshop ashore for overhaul by approved. • Dismantling and calibration. • Dismantling and inspecting suction and puncture valves. • Light grinding and/or lapping of all suction valves and puncture valve/seats. • Reassemble pumps (Qty:__) • Replacing damaged or worn out parts to be replaced as per instruction from Owner's representative. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ME Scavenge air coolers | Machinery main components | MM03 |  | Approved | Minor | 20/01/2070 | 26/01/2070 | Scope of work: • Safely remove the scavenge air coolers from the main engine in accordance with the manufacturer's guidelines. • Transport the coolers to an approved facility for cleaning. • Perform thorough cleaning using a chemical bath or ultrasonic methods to remove all contaminants. • Conduct a detailed inspection of the coolers for any signs of wear, corrosion, or damage. • Pressure test. • Modify the existing flanges on the air coolers: o Machine a groove into each flange to accommodate a new sealing method o Ensure the groove is suitable for a rubber seal with a diameter as required by the engine specifications • Clean the housing of the coolers to remove dirt, oil, and debris.. • Apply a fresh coat paint to the housing. • Refit the cleaned and inspected coolers back onto the main engine. • Ensure all connections and seals are secure and leak-free. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ME Aux blowers | Machinery main components | MM04 |  | Approved | Minor | 20/01/2071 | 26/01/2071 | Scope of work: • Megger testing of fan motors across phases and to ground prior to starting dismantling of fan units. • Removal and subsequent refitting of fan unit. • Transporting fan unit to and from shore workshop. • Dismantling of the motor. • Chemical cleaning and water washing of rotor and stator windings. • Megger testing of windings and providing results to Owner's representative. • Calibration of bearing housings, shaft bearing and coupling landings results to be presented to owner's representative. • Assembly of motor with new bearings. • Renewal of shaft seals with Owner’s supply spares. • Refitting of motor and fitting of fan. • Balancing of fan unit in workshop when built up. • Test run for acceptance by Owner's representative. Yard to quote separately for: 1. Machining and sleeving of bearing housings with a steel sleeve. 2. Machining and sleeving of motor shaft in the area of bearings and coupling landings, using a shrink-fit method. 3. In the event of low insulation resistance readings, provide revarnishing to Class F standards and oven baking of windings. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ME Air receiver | Machinery main components | MM05 |  | Approved | Minor | 20/01/2072 | 26/01/2072 | Scope of work: • Remove and subsequently refit scavenge space doors. • Remove and subsequently refit scavenge trunking end cover door(s). • Perform comprehensive cleaning of the under-piston scavenge space and scavenge receiver space. • Provide disposal certificates for all cleaning materials, oil, sludge, and sediments. • Ensure that all spaces are ready and available for inspection by the Owner’s representative before closing. • Include provision of all necessary temporary lighting for the duration of the maintenance works. Including: • Overhaul of scavenge air receivers (Qty:__) • Removal and disposal of sludge |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ME Bearings | Machinery main components | MM06 |  | Approved | Minor | 20/01/2073 | 26/01/2073 | Scope of work: 1. Bottom end bearings (connection rod bearings) a. Taking a full set of bottom end bearing clearances. Clearance report to be presented to Owner's representative. b. Opening up and subsequently closing of bearing to allow inspection of bearing shells and journal by Class Surveyor and Owner's representative. Taking final clearance. Clearance report to be presented to owner's representative. c. Also quote for: i. Replacement of bearings ii. Polishing of bearing journal to give surface finish of 5 micron 2. Main bearings a. Measuring and recording all main bearing clearances using "Swedish feeler" gauges. Measure height of bearing top keep ford and aft port to starboard (4) points. Ensure clearances conform to clearances in Maker’s manual. Check from vessel records as to "mark" of main bearing fitted at each journal. Clearance report to be presented to Owner's representative. b. Dismantling main bearing cap and oil pipes. Removing bearing top half and lifting out from engine. Ensure precautions taken to protect bearing shell horns and landing faces. Turning out main bearing shell bottom half using special tools provide to allow inspection for survey of the top and bottom bearing halves and crankshaft journal. Reassembling bearing as per supervising engineer's requirements. Taking final bearing clearances, these are to be witnessed by Owner’s representative and clearance report presented to Owner’s representative. c. Also quote for: i. Replacement of bearings ii. Polishing of bearing journal to give surface finish of 5 micron 3. Crosshead bearings a. Measuring and recording all crosshead bearing clearance using "Swedish feeler" gauges before starting bearing work. b. Dismantling cross head bearing in situ to allow inspection for survey of the top and bottom bearing halves and cross-head pin. Reassembling bearing and cross head assembly as per supervising engineer's requirements. Taking final bearing clearances, these are to be witnessed by Owner’s representative and clearance report presented to Owner’s representative. c. Also quote for: i. Replacement of bearings ii. Polishing of bearing journal to give surface finish of 5 micron 4. Crosshead guides a. Measuring and recording all cross-head guide clearances. Turning the piston to approximately mid stroke and using feeler gauges to measure the clearance of the crosshead guide at the top, center and bottom of the forward and aft sides, P & S. The clearance is the total of the Port and Starboard measurements for each point. Clearance report presented to Owner’s representative. On completion of any bearing work another complete set of clearances will be taken. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ME Thrust bearing | Machinery main components | MM07 |  | Approved | Minor | 20/01/2074 | 26/01/2074 | Scope of work: 1. Measuring and recording the thrust bearing clearance using a magnetic stand and dial indicator gauge. The clearance is the movement of the collar as the shaft is pushed against the forward and aft pads alternatively. Yard to supply necessary hydraulic jack for positioning crankshaft collar against thrust pads. Compare readings to vessel's records and initial "record of inspection". 2. Visually inspecting the condition of the collar faces. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Exhaust gas economizer | Machinery main components | MM08 |  | Approved | Minor | 20/01/2075 | 26/01/2075 | Scope of work: 1. Exhaust Boiler / Exhaust Gas Economizer is to be opened up for inspection - both water and smoke sides. All mountings identified by CE that are not already surveyed to be disassembled and dismantled /overhauled. 2. Present for survey and to assemble everything back with new jointing’s and gland packings wherever required. 3. Boiler to be fill up and make ready for usage. 4. All mountings to be surveyed by Class surveyor, and safety valves tested & adjusted. 5. Safety valves to be floated later at sea. 6. Pressure gauge to be tested & calibrated. 7. Soot blowing system to be checked internally for pipes, lances and glands. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Crankshaft Deflections | Machinery main components | MM09 |  | Approved | Minor | 20/01/2076 | 26/01/2076 | Taking Main Engine Crankcase Deflection readings. Two sets of readings. 1. Before docking with the vessel afloat but within the dry-dock. 2. Upon completion of all engine works with the vessel afloat. Allow for opening and subsequent closing of <twelve (12)> crankcase doors per engine. Your tender shall allow for all necessary lighting and ventilation. Report of readings to be presented to Owners Representative. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HFO settling tanks | System for machinery main components | SM01 |  | Approved | Minor | 20/01/2077 | 26/01/2077 | Scope of work: 1. Cleaning of entire tank to a standard suitable for hot work on adjacent bulkhead. 2. Removal and disposal of un-pumpable heavy oil. 3. Removal and disposal of any sludge from tank. Must be in accordance with environmental regulations and certificates of disposal are to be provided to Owner’s representative. Include all ventilation, gas free certificates, hot work certification, temperature, lighting, cleaning equipment including tank hoist. Including: • General cleaning • Open/close manholes (Qty:__) • Chemist Gas free certificate, initial visit • Gas free certificate, additional visits • Gas free fan/blower connected/disconnected (Qty:__) • Fan, usage (Qty:__) • Light • Disposal of sludge |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HFO service tanks | System for machinery main components | SM02 |  | Approved | Minor | 20/01/2078 | 26/01/2078 | Scope of work: 1. Cleaning of entire tank to a standard suitable for hot work on adjacent bulkhead. 2. Removal and disposal of un-pumpable heavy oil. 3. Removal and disposal of any sludge from tank. Must be in accordance with environmental regulations and certificates of disposal are to be provided to Owner’s representative. Include all ventilation, gas free certificates, hot work certification, temperature, lighting, cleaning equipment including tank hoist. Including: • General cleaning • Open/close manholes (Qty:__) • Chemist Gas free certificate, initial visit • Gas free certificate, additional visits • Gas free fan/blower connected/disconnected (Qty:__) • Fan, usage (Qty:__) • Light • Disposal of sludge |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sludge tank cleaning | System for machinery main components | SM03 |  | Approved | Minor | 20/01/2079 | 26/01/2079 | Scope of work: 1. Cleaning of entire tanks for inspection 2. Pressure testing of tank heating coils 3. Pumping out and disposal of sludge 4. Removal of sludge residues from each tank 5. Scraping in tanks 6. Disposal of sludge residues in accordance with environmental regulations and certificates of disposal are to be provided to Owner’s representative. Include all ventilation, gas free certificates, hot work certification, temperature, lighting, cleaning equipment including tank hoist. Including: • Tank cleaning • Ventilation and Light • Chemist Gas free inspection/certificate • Pressure testing • Disposal of sludge • Scraping |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bilge holding tank cleaning | System for machinery main components | SM04 |  | Approved | Minor | 20/01/2080 | 26/01/2080 | Scope of work: 1. Cleaning of entire tanks for inspection 2. Pressure testing of tank heating coils 3. Pumping out and disposal of sludge 4. Removal of sludge residues from each tank 5. Scraping in tanks 6. Disposal of sludge residues in accordance with environmental regulations and certificates of disposal are to be provided to Owner’s representative. Include all ventilation, gas free certificates, hot work certification, temperature, lighting, cleaning equipment including tank hoist. Including: • Tank cleaning • Ventilation and Light • Chemist Gas free inspection/certificate • Pressure testing • Disposal of dirty water • Disposal of sludge • Scraping |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main circuit breakers | Common systems | CS01 |  | Approved | Minor | 20/01/2081 | 26/01/2081 | Scope of work: 1. Removal from the switchboard and transportation to shore workshops for completion of the below works. Return and reinstallation back into the switchboard. 2. All Contacts to be examined and checked for wear. Any defective contacts are to be replaced. 3. Arc Chutes are to be examined. Any damaged arc chutes are to be replaced. 4. All Connections to be checked for tightness. 5. Carbon impressions recorded. 6. Upon completion of all the above works, all the trip functions built into the circuit breaker are to be tested and calibrated by simulation with current injection equipment or other suitable means acceptable to the class surveyor and owners representative. Test reports and certificates are to be submitted to the owner’s representative. Including: • Transport to and from workshop • Examine contacts • Examine arc chutes • Check connections for tightness • Record carbon impressions • Test trip functions |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Switchboard cleaning | Common systems | CS02 |  | Approved | Minor | 20/01/2082 | 26/01/2082 | Scope of work: 1. Opening up all switchboard panels and removal of necessary protective covers and screens as directed by the Owner’s representative. 2. Conduct a detailed inspection of all electrical components within the switchboards for signs of wear, corrosion, or damage. Check and secure the tightness of all electrical connections, including bus bars, terminals, and contact points. 3. Carry out vacuum cleaning to remove dust, debris, and any foreign objects from within the switchboard enclosures. Use only non-conductive cleaning tools and materials suitable for electrical equipment to prevent damage and ensure safety. 4. Replace all covers, screens, and protective barriers removed during the cleaning process. Perform a functional test of the switchboard operations to confirm that all components are functioning correctly after maintenance. Scheduling and Coordination: • Coordinate with the Owner’s representative to schedule the work at a time that minimizes disruption to the ship's operations. • Provide all necessary temporary lighting and ventilation for the duration of the maintenance work. Including: • Remove protective covers • Inspect and check tightness • Vacuum cleaning • Replace protective covers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0