## Caroline
M/V Palmerton (NB 0301 / Typ PK 116)
Change of crane wires |  |  |  |  | Date of commissioning: | 2009-12-07
[7 empty] | date of last inspection | result of last inspection/comments | wire replacement planned |  | done | next suggested inspection
Crane #1 | initial | 1st replacement | 2nd replacement | 3rd replacement | 4th replacement | 5th replacment |  |  | when | where | done
Luffing wire | 2009-12-07 | 2016-06-22 |  |  |  |  | 2016-05-18 | to be condemned, severity rating 120% | 2016-06-22 | Rotterdam | x | July 2020
Hoisting wire | 2009-12-07 | 2016-06-26 | 2019-06-06
Aux. wire | 2009-12-07 | July 16 | 2023-02-01 |  |  |  | 2016-05-18 | to be condemned, severity rating 100% | July 16 | at sea | x | July 2020
Crane #2
Luffing wire | 2009-12-07 | 2016-06-23 |  |  |  |  | 2016-05-18 | to be condemned, severity rating 125% | 2016-06-23 | Rotterdam | x | July 2020
Hoisting wire | 2009-12-07 | 2016-06-23 | 2020-08-01 |  |  |  | 2016-05-18 | to be condemned, severity rating 189% | 2016-06-23 | Rotterdam | x | July 2020
Aux. wire | 2009-12-07 | July 16 |  |  |  |  | 2016-05-18 | limited use, severity rating 80 % | July 16 | at sea | x | July 2020
Gangway wire S/S |  | 2019-09-01 | [5 empty] | report saved under
Gangway wire P/S |  | 09/.2019
Rescueboat (L. raft) | N/A | N/A | N/A
Rescueboat (Boat + L.Raft) | 2009-12-01 | 2014-09-01 | 2019-08-01
Liferaft | N/A | N/A | N/A
Freefallboat (PS) | N/A | N/A | N/A
Freefallboat (SB) | 2009-12-01 | 2014-11-01 | 2019-09-01 |  |  |  | date of last load test | result of the load test saved under |  | location
Facts & Figure
| Crane #1 |  | Crane #2
Wires | Dia. in mm | Length in m | Dia. in mm | Length in m
Luffing wire | 50 | 431 | 50 | 431
Hoisting wire | 70 | 330 | 70 | 330
Auxiliary hoist wire | 34 | 160 | 34 | 160
Wires | Dia. in mm | Length in m | SWL in mt
Provision | na |  | Crane #1 | 450 | Provision | na
Rescueboat (Prov.) | na |  | Crane #2 | 450 | R.Boat (Prov.) | na
Rescueboat (Boat) | 12 | 38 | Aux. Hoist #1 | 35 | R.Boat (Boat) | 2.1
Liferaft | 12 | 38 | Aux. Hoist #2 | 35 | Liferaft | 2.1
Freefallboat (PS) | na |  |  |  | Freefallboat | 5.2
Freefallboat (SB) | 18 | 30
Date: | 2023-02-27 |  |  |  | checked: | 2012-01-25

## Amoenitas
M/V Amoenitas (NB 0305 / Typ PK 116)
Change of crane wires |  |  |  |  | Date of commissioning: | 2010-11-22
[7 empty] | date of last inspection | kind/result of inspection - comments | wire replacement planned |  | done | next suggested inspection
Crane #1 | initial | 1st replacement | 2nd replacement | 3rd replacement | 4th replacement | 5th replacment |  |  | when | where
Luffing wire | 2010-10-18 | 2016-05-17 |  |  |  |  | 2016-04-06 | limited use, severity rating 98 % | 2016-05-17 | Rostock | x | July 2020
Hoisting wire | 2010-10-18 | 2016-05-17 | 2018-05-21 |  |  |  | 2016-04-06 | to be condemned, severity rating 131 % | 2016-05-17 | Rostock | x | July 2020
Aux. wire | 2010-10-18 | 2015-05-29
Crane #2
Luffing wire | 2010-10-18 | 2016-05-17 |  |  |  |  | 2016-04-06 | to be condemned, severity rating 128 % | 2016-05-17 | Rostock | x | July 2020
Hoisting wire | 2010-10-18 | 2016-05-17 | 2019-02-01 | 2020-08-01
Aux. wire | 2010-10-18 | 2017-12-14 | 2021-04-01
Gangway wire S/S |  |  | 2017-03-01 |  |  |  |  | report saved under
Gangway wire P/S |  |  | 2017-03-01
Rescueboat (L. raft) | N/A | N/A | N/A
Rescueboat (Boat + L.Raft) | 2010-06-02 | 2015-09-02 | 2020-12-01
Liferaft | N/A | N/A | N/A
Freefallboat (PS) | N/A | N/A | N/A
Freefallboat (SB) | 2010-07-01 | 2015-09-02 | 2020-12-01 |  |  |  | date of last load test | result of the load test saved under |  | location
Facts & Figure
| Crane #1 |  | Crane #2
Wires | Dia. in mm | Length in m | Dia. in mm | Length in m
Luffing wire | 50 | 431 | 50 | 431
Hoisting wire | 70 | 330 | 70 | 330 |  |  | Remarks:
Auxiliary hoist wire | 34 | 160 | 34 | 160 |  |  | 1. | On both cranes luffing wire sheaves middle boom replaced
[7 empty] | 2. | Crane 2 luffing wire sheaves on crane top replaced
Wires | Dia. in mm | Length in m | SWL in mt |  |  |  | 3. | Loadcell Crane#2 needs replacment
Provision | n/a |  | Crane #1 | 450 | Provision | n/a
Rescueboat (Prov.) | 12 | 40 | Crane #2 | 450 | R.Boat (Prov.) | 1.3
Rescueboat (Boat) | 12 | 40 | Aux. Hoist #1 | 35 | R.Boat (Boat) | 1.3
Liferaft | 12 | 40 | Aux. Hoist #2 | 35 | Liferaft | 1.3
Freefallboat (PS) | n/a |  |  |  | Freefallboat | 5.4
Freefallboat (SB) | 18 | 30
Date: | 2018-10-18 |  |  |  | checked: | 2018-10-18
| 2021-06-17 |  |  |  |  | 2021-06-17

## Hilke
M/V Palabora (NB 0302 / Typ PK 116)
Change of crane wires |  |  |  |  | Date of commissioning: | 2010-02-10
[7 empty] | date of last inspection | kind/result of inspection - comments | wire replacement planned |  | done | next suggested inspection
Crane #1 | initial | 1st replacement | 2nd replacement | 3rd replacement | 4th replacement | 5th replacment |  |  | when | where
Luffing wire | 2010-02-10 | 2017-01-31 |  |  |  |  | 2016-03-28 | useless inspection, were later inspected by Pfeifer | 2017-01-31 | Singapore | x
Hoisting wire | 2010-02-10 | 2017-01-31 | 2021-09-01 |  |  |  | 2016-03-28 | useless inspection, were later inspected by Pfeifer | 2017-01-31 | Singapore | x
Aux. wire | 2010-02-10 | 2016-09-01 |  |  |  |  | 2021-09-18 | Ex Amoe.Wire Manuf.Year 02.2019/Inst.Hilke 09.2021
Crane #2
Luffing wire | 2010-02-10 | 2017-01-31 |  |  |  |  | 2016-03-28 | useless inspection, were later inspected by Pfeifer | 2017-01-31 | Singapore | x
Hoisting wire | 2010-02-10 | 2017-01-31 |  |  |  |  | 2016-03-28 | useless inspection, were later inspected by Pfeifer | 2017-01-31 | Singapore | x
Aux. wire | 2010-02-10 | 2016-09-01
Gangway wire S/S |  | 2019-12-01 | [5 empty] | report saved under
Gangway wire P/S |  | 2019-12-01
Rescueboat (L. raft) | N/A | N/A
Rescueboat (Boat + L.Raft) | 2011-02-01 | 2015-01-01
Liferaft | N/A | N/A
Freefallboat (PS) | N/A | N/A
Freefallboat (SB) | 2011-02-01 | 2015-01-01 |  |  |  |  | date of last load test | result of the load test saved under |  | location
Facts & Figure | [6 empty] | 2019-04-08 | G:\Heavylift\2-Service Reports\8005 Hilke (ex Palabora)\Cranes |  | Shanghai
| Crane #1 |  | Crane #2
Wires | Dia. in mm | Length in m | Dia. in mm | Length in m
Luffing wire | 50 | 431 | 50 | 431
Hoisting wire | 70 | 330 | 70 | 330
Auxiliary hoist wire | 34 | 160 | 34 | 160
Wires | Dia. in mm | Length in m | SWL in mt
Provision |  |  | Crane #1 | 450 | Provision
Rescueboat (Prov.) |  |  | Crane #2 | 450 | R.Boat (Prov.)
Rescueboat (Boat) | 12 | 40 | Aux. Hoist #1 | 35 | R.Boat (Boat) | 2.1
Liferaft |  |  | Aux. Hoist #2 | 35 | Liferaft
Freefallboat (PS) |  |  |  |  | Freefallboat | 2.2
Freefallboat (SB) | 18 | 30
Date: | 2016-03-31 |  |  |  | checked: | 2012-01-25

## Anna
M/V Anna (NB 0303 / Typ PK 116)
Change of crane wires |  |  |  |  | Date of commissioning: | 2010-05-25
[7 empty] | date of last inspection | kind/result of inspection - comments | wire replacement planned |  | done | next suggested inspection
Crane #1 | initial | 1st replacement | 2nd replacement | 3rd replacement | 4th replacement | 5th replacment |  |  | when | where
Luffing wire | 2010-05-25 | 2016-04-09 |  |  |  |  | 2019-02-01 | Visual- no indications of significance were found
Hoisting wire | 2010-05-25 | 2015-03-21 | 2019-09-01 | 2022-03-01
Aux. wire | 2010-05-25 | 2015-05-24 |  |  |  |  | 2019-02-01 | Visual- severity rating 100 % | next possibility
Crane #2
Luffing wire | 2010-05-25 | 2018-04-14 |  |  |  |  | 2019-02-01 | Visual - no indications of significance were found
Hoisting wire | 2010-05-25 | 2014-06-25 | 2019-07-01 |  |  |  | 2019-07-23 | unfit for service (see report), wire of crane 1 is taken | 2019-07-25 | Singapore | x
Aux. wire | 2010-05-25 | 2014-03-07 | 2019-05-01 |  |  |  | 2019-02-01 | Visual - severity rating 40 %
Gangway wire S/S | 04./2018 | [6 empty] | report saved under
Gangway wire P/S | 04./2018 | [5 empty] | 2019-02-01 | G:\Heavylift\2-Service Reports\8006 Anna (ex. Palembang)\Cranes
Rescueboat (L. raft) | N/A | N/A | N/A |  |  |  | 2019-07-23 | G:\Heavylift\2-Service Reports\8006 Anna (ex. Palembang)\Cranes
Rescueboat (Boat + L.Raft) | 2010-05-01 | 2015-03-01 | 2020-02-01
Liferaft | N/A | N/A | N/A
Freefallboat (PS) | N/A | N/A | N/A
Freefallboat (SB)-Aft | 2010-05-01 | 2018-03-01 |  |  |  |  | date of last load test | result of the load test saved under |  | location
Facts & Figure
| Crane #1 |  | Crane #2
Wires | Dia. in mm | Length in m | Dia. in mm | Length in m
Luffing wire | 50 | 431 | 50 | 431
Hoisting wire | 70 | 330 | 70 | 330
Auxiliary hoist wire | 34 | 160 | 34 | 160
Wires | Dia. in mm | Length in m | SWL in mt
Provision | N/A | N/A | Crane #1 | 450 | Provision | N/A
Rescueboat (Prov.) | N/A | N/A | Crane #2 | 450 | R.Boat (Prov.) | N/A
Rescueboat (Boat) | 12 | 38 | Aux. Hoist #1 | 35 | R.Boat (Boat) | N/A
Liferaft | N/A | N/A | Aux. Hoist #2 | 35 | Liferaft | N/A
Freefallboat (PS) | N/A | N/A |  |  | Freefallboat | N/A
Freefallboat (SB) | 18 | 30
Date: | 2018-10-18 |  |  |  | checked: | 2018-10-18

## Imke
M/V Imke (NB 0304 / Typ PK 116)
Change of crane wires |  |  |  |  | Date of commissioning: | 2010-08-06
[7 empty] | date of last inspection | kind/result of inspection - comments | wire replacement planned |  | done | next suggested inspection
Crane #1 | initial | 1st replacement | 2nd replacement | 3rd replacement | 4th replacement | 5th replacment |  |  | when | where
Luffing wire | 2010-07-18 | 2019-03-01 |  |  |  |  | 2016-04-17 | further use, severity rating 24 % | in 2018 |  | x
Hoisting wire | 2010-07-18 | 2017-11-10 | 2022-12-01 |  |  |  | 2016-04-17 | to be condemned, severity rating 238 % | 2017-10-06 |  | x
Aux. wire | 2010-07-18 | 2016-05-17 |  |  |  |  | 2016-04-17 | to be condemned, severity rating 140 % | 2016-05-17 | at sea | x
Crane #2
Luffing wire | 2010-07-18 | 2019-03-01 |  |  |  |  | 2016-04-17 | further use, severity rating 44 % | in 2018 |  | x
Hoisting wire | 2010-07-18 | 2017-11-10 |  |  |  |  | 2016-04-17 | to be condemned, severity rating 215 % | 2017-10-06 |  | x
Aux. wire | 2010-07-18 | 2016-05-13 |  |  |  |  | 2016-04-17 | to be condemned, sevirity rating 420 % | 2016-05-13 | at sea | x
Gangway wire S/S | N/A | 2020-11-01 | [5 empty] | report saved under
Gangway wire P/S | N/A | 2020-11-01
Rescueboat (L. raft) | N/A | N/A
Rescueboat (Boat + L.Raft) | 2010-07-01 | 2015-01-01 | 2020-01-01
Liferaft | N/A | N/A | N/A
Freefallboat (SB) | 2010-07-01 | 2015-05-01 | 2017-11-01
Freefallboat (PS) | N/A | N/A | N/A |  |  |  | date of last load test | result of the load test saved under |  | location
Facts & Figure
| Crane #1 |  | Crane #2
Wires | Dia. in mm | Length in m | Dia. in mm | Length in m
Luffing wire | 50 | 431 | 50 | 431
Hoisting wire | 70 | 330 | 70 | 330
Auxiliary hoist wire | 34 | 160 | 34 | 160
Wires | Dia. in mm | Length in m | SWL in mt
Provision | N/A | N/A | Crane #1 | 450 | Provision | N/A
Rescueboat (Prov.) | N/A | N/A | Crane #2 | 450 | R.Boat (Prov.) | N/A
Rescueboat (Boat) | 12 | 38 | Aux. Hoist #1 | 35 | R.Boat (Boat) | 2.1
Liferaft | N/A | N/A | Aux. Hoist #2 | 35 | Liferaft | N/A
Freefallboat (SB) | 18 | 30 |  |  | Freefallboat | 3,1
Freefallboat (PS) | N/A | N/A
Date: | 2018-10-17 |  |  |  | checked: | 2018-10-17

## Calypso
M/V Calypso (NB 0306 / Typ PK 116)
Change of crane wires |  |  |  |  | Date of commissioning: | 2011-02-28
[7 empty] | date of last inspection | kind/result of inspection - comments | wire replacement planned |  | done | next suggested inspection
Crane #1 | initial | 1st replacement | 2nd replacement | 3rd replacement | 4th replacement | 5th replacment |  |  | when | where
Luffing wire | 2011-02-28 | 2016-11-02 |  |  |  |  | 2016-03-09 | to be condemned, severity rating 248 % | 2016-11-02 |  | x
Hoisting wire | 2011-02-28 | 2016-11-02 | 2022-11-01 |  |  |  | 2016-03-09 | to be condemned, severity rating 196 % | 2016-11-02 |  | x
Aux. wire | 2011-02-28 | 2014-02-12 | 2021-04-01
Crane #2
Luffing wire | 2011-02-28 | 2016-11-02 |  |  |  |  | 2016-03-09 | to be condemned, severity rating 177 % | 2016-11-02 |  | x
Hoisting wire | 2011-02-28 | 2016-11-02 | 2021-02-01 |  |  |  | 2016-03-09 | further use, severity rating 40 % | 2016-11-02 |  | x
Aux. wire | 2011-02-28 | 2015-03-29 | 2021-04-01
Gangway wire S/S | [7 empty] | report saved under
Gangway wire P/S
Rescueboat (L. raft) | N/A | N/A
Rescueboat (Boat + L.Raft) | 2011-02-01 | 2021-01-01
Liferaft | N/A | N/A
Freefallboat (PS) | N/A | N/A
Freefallboat (SB) | 2021-02-01 | 2021-01-01 |  |  |  |  | date of last load test | result of the load test saved under |  | location
Facts & Figure
| Crane #1 |  | Crane #2
Wires | Dia. in mm | Length in m | Dia. in mm | Length in m
Luffing wire | 50 | 431 | 50 | 431
Hoisting wire | 70 | 330 | 70 | 330
Auxiliary hoist wire | 34 | 160 | 34 | 160
Wires | Dia. in mm | Length in m | SWL in mt
Provision | N/A | N/A | Crane #1 | 450 | Provision | N/A
Rescueboat (Prov.) | N/A | N/A | Crane #2 | 450 | R.Boat (Prov.) | N/A
Rescueboat (Boat) | 12 | 40 | Aux. Hoist #1 | 35 | R.Boat (Boat)
Liferaft |  |  | Aux. Hoist #2 | 35 | Liferaft
Freefallboat (PS) | N/A | N/A |  |  | Freefallboat
Freefallboat (SB) | 18 | 30
Date: | 2016-03-31 |  |  |  | checked: | 2012-01-25

## Combi Dock I
M/V Combi Dock I (NB 112 / Type Dock Ship)
Change of crane wires |  |  |  |  | Date of commissioning: | 2008-01-20
[7 empty] | date of last inspection | kind/result of inspection - comments | wire replacement planned |  | done | next suggested inspection
Crane #1 | initial | 1st replacement | 2nd replacement | 3rd replacement | 4th replacement | 5th replacement |  |  | when | where | done
Luffing wire | 2008-01-20 | 2013-05-30 |  |  |  |  | 2019-09-10 | visual inspection by Pfeifer
Hoisting wire | 2008-01-20 | 2010-12-08 | Q1/2021 |  |  |  | 2019-09-10 | visual inspection by Pfeifer
Aux. wire | 2008-01-20 | 2012-01-30 | 2018-03-12 |  |  |  | 2019-09-10 | visual inspection by Pfeifer
Crane #2
Luffing wire | 2008-01-20 | 2013-05-30 |  |  |  |  | 2019-09-10 | visual inspection by Pfeifer
Hoisting wire | 2008-01-20 | 2010-12-08 |  |  |  |  | 2019-09-10 | visual inspection by Pfeifer
Aux. wire | 2008-01-20 | 2013-05-30 |  |  |  |  | 2019-09-10 | visual inspection by Pfeifer
Crane #3
Luffing wire | 2008-01-20 | 2017-07-17 |  |  |  |  | 2019-09-10 | visual inspection by Pfeifer
Hoisting wire | 2008-01-20 | 2013-05-30 |  |  |  |  | 2019-09-10 | visual inspection by Pfeifer
Aux. wire | 2008-01-20 | 2013-05-30 |  |  |  |  | 2019-09-10 | visual inspection by Pfeifer
Provision | N/A | [6 empty] | report saved under
[7 empty] | 2019-09-10 | G:\Heavylift\2-Service Reports\74 Combi Dock I\Crane wires
Rescueboat (L. raft) | N/A
Rescueboat (Boat) | N/A
Liferaft | N/A
Freefallboat (PS) | N/A
Freefallboat (SB) | N/A | [5 empty] | date of last load test | result of the load test saved under |  | location
Facts & Figure
| Crane #1 |  | Crane #2 |  | Crane #3
Wires | Dia. in mm | Length in m | Dia. in mm | Length in m | Dia. in mm | Length in m
Luffing wire | 50 | 260 | 50 | 260 | 42 | 300
Hoisting wire | 76 | 178 | 76 | 178 | 70 | 175
Auxiliary hoist wire | 34 | 160 | 34 | 160 | 25 | 130
Wires | Dia. in mm | Length in m | SWL in mt
Provision |  |  | Crane #1 | 350 | Provision
Rescueboat (Prov.) |  |  | Crane #2 | 350 | R.Boat (Prov.)
Rescueboat (Boat) |  |  | Crane #3 | 200 | R.Boat (Boat)
Liferaft |  |  | Aux. Hoist #1 | 35 | Liferaft
Freefallboat (PS) |  |  | Aux. Hoist #2 | 35 | Freefallboat
Freefallboat (SB) |  |  | Aux. Hoist #3 | 10
Remarks:
Date: | 2018-10-18

## Panagia
M/V Panagia (NB 328 / Typ CL500)
Change of crane wires |  |  |  |  | Date of commissioning: | 2004-04-26
[7 empty] | date of last inspection | kind/result of inspection - comments | wire replacement planned |  | done | next suggested inspection
Crane #1 | initial | 1st replacement | 2nd replacement | 3rd replacement | 4th replacement | 5th replacment |  |  | when | where
Luffing wire | 2004-04-26 | 2009-09-13 | 2019-02-01
Hoisting wire | 2004-04-26 | 2009-09-11 | 2019-02-01
Aux. wire | 2004-04-26 | 2012-07-27 | 2019-02-01
Crane #2
Luffing wire | 2004-04-26 | 2009-09-12 | 2019-02-01
Hoisting wire | 2004-04-26 | 2009-07-14 | 2019-02-01
Aux. wire | 2004-04-26 | 2007-09-20 |  |  |  |  | 2018-02-21 | NDT inspection by Premiera Scana Technology - Wire is Fit for Continued Use with regards to segment sampled. Due to Wire Rope reeving system, external wires at Hook ends cannot be fully assessed.
Provision |  |  | 2017-12-01 |  |  |  |  | report saved under
Rescueboat (L. raft) |  |  | 2017-07-01
Rescueboat (Boat) |  |  | N/A
Liferaft |  |  | N/A
Freefallboat (PS) |  |  | N/A
Freefallboat (SB) |  |  | N/A |  |  |  | date of last load test | result of the load test saved under |  | location
Facts & Figure
| Crane #1 |  | Crane #2
Wires | Dia. in mm | Length in m | Dia. in mm | Length in m
Luffing wire | 38 | 277 | 38 | 277
Hoisting wire | 66 | 195 | 66 | 195
Auxiliary hoist wire | 32 | 175 | 32 | 175
Wires | Dia. in mm | Length in m | SWL in mt
Provision | 13 | 69 | Crane #1 | 250 | Provision | 5
Rescueboat (Prov.) | N/A |  | Crane #2 | 250 | R.Boat (Prov.) | N/A
Rescueboat (Boat) | 14 | 25 | Aux. Hoist #1 | 35 | R.Boat (Boat) | 1.427
Liferaft | N/A |  | Aux. Hoist #2 | 35 | Liferaft | N/A
Freefallboat (PS) | N/A |  |  |  | Freefallboat | N/A
Freefallboat (SB) | N/A
Date: | 2016-03-31 |  |  |  | checked: | 2012-01-25

## Pantanal
M/V Pantanal (NB 337 / Typ CL500)
Change of crane wires |  |  |  |  | Date of commissioning: | 2004-07-26
[7 empty] | date of last inspection | kind/result of inspection - comments | wire replacement planned |  | done | next suggested inspection
Crane #1 | initial | 1st replacement | 2nd replacement | 3rd replacement | 4th replacement | 5th replacment |  |  | when | where
Luffing wire | 2004-07-26 | 2015-07-16 |  |  |  |  | 2018-08-11 | Annual examination of IC and Loose Gear by DNV-GL / Satisfactory | 16.07.20 | NA |  | 11.08.19
Hoisting wire | 2004-07-26 | 2012-10-12 | 2018-12-12 |  |  |  | 2018-08-11 | Annual examination of IC and Loose Gear by DNV-GL / Satisfactory | 2018-12-12 | Drydock | x
Aux. wire | 2004-07-26 | 2015-07-16 | 2016-11-17 |  |  |  | 2018-08-11 | Annual examination of IC and Loose Gear by DNV-GL / Satisfactory | 17.11.21 | NA |  | 11.08.19
Crane #2
Luffing wire | 2004-07-26 | 2015-07-15 |  |  |  |  | 2018-08-11 | Annual examination of IC and Loose Gear by DNV-GL / Satisfactory | 15.07.20 | NA |  | 11.08.19
Hoisting wire | 2004-07-26 | 2012-10-12 | 2018-04-10 |  |  |  | 2018-08-11 | Annual examination of IC and Loose Gear by DNV-GL / Satisfactory | 10.04.23 | NA |  | 11.08.19
Aux. wire | 2004-07-26 | 2011-05-21 | 2016-11-17 | 2018-04-10 |  |  | 2018-08-11 | Annual examination of IC and Loose Gear by DNV-GL / Satisfactory | 10.04.23 | NA |  | 11.08.19
Provision | 2004-07-26 | 2011-07-07 | 2017-03-03 |  |  |  |  | report saved under
Rescueboat (L. raft) | 2004-07-26 | 2014-05-01 | 2018-01-30
Rescueboat (Boat) | NA | NA | NA | NA | NA | NA
Liferaft | 2004-07-26 | 2014-05-01 | 2018-01-30
Freefallboat (PS) | NA | NA | NA | NA | NA | NA
Freefallboat (SB) | 2004-07-26 | 2011-07-07 | 2017-03-03 |  |  |  | date of last load test | result of the load test saved under |  | location
Facts & Figure
| Crane #1 |  | Crane #2
Wires | Dia. in mm | Length in m | Dia. in mm | Length in m
Luffing wire | 38 | ~200 | 38 | ~200
Hoisting wire | 66 | 195 | 66 | 0
Auxiliary hoist wire | 32 | 175 | 32 | 175
Wires | Dia. in mm | Length in m | SWL in mt
Provision | 13 | 69 | Crane #1 | 250 | Provision | 5
Rescueboat (Prov.) | 14 | 25 | Crane #2 | 250 | R.Boat (Prov.) | 3
Rescueboat (Boat) | 14 | 25 | Aux. Hoist #1 | 35 | R.Boat (Boat) | 3
Liferaft | 14 | 25 | Aux. Hoist #2 | 35 | Liferaft | 3
Freefallboat (PS) | NA | NA |  |  | Freefallboat | 5
Freefallboat (SB) | 13 | 69
Date: | 16.10.2018 |  |  |  | checked:

## Annemieke
M/V Annemieke (NB 1121 / Type 161)
Change of crane wires |  |  |  |  | Date of commissioning: | 1998-04-01
[7 empty] | date of last inspection | kind/result of inspection - comments | wire replacement planned |  | done | next suggested inspection
Crane #1 | initial | 1st replacement | 2nd replacement | 3rd replacement | 4th replacement | 5th replacement |  |  | when | where | done
Luffing wire | 1998-03-01 | 2003-05-01 | 2007-03-01 | 2012-07-01 | 2018-09-01
Hoisting wire | 1998-03-01 | 2003-05-01 | 2007-03-01 | 2012-07-01 | 2018-09-01
Aux. wire | 1998-03-01 | 2006-07-01 | 2012-07-01 |  | 2022-05-01
Crane #2
Luffing wire | 1998-03-01 | 2003-05-01 | 2007-03-01 | 2012-07-01 | 2022-05-01 |  | 2018-09-01 | NDT - no indications of significance were found
Hoisting wire | 1998-03-01 | 2003-05-01 | 2007-03-01 | 2012-07-01 | 2022-05-01 |  | 2018-09-01 | NDT - no indications of significance were found
Aux. wire | 1998-03-01 | 2000-08-01 | 2009-06-01 | 2012-07-01 | 2022-05-01
Crane #3
Luffing wire | 1998-03-01 | 2003-05-01 | 2007-03-01 | 2012-07-01 | 2022-05-01 |  | 2018-09-01 | NDT - no indications of significance were found
Hoisting wire | 1998-03-01 | 2003-05-01 | 2007-03-01 | 2012-07-01 | 2018-09-01
Aux. wire | 1998-03-01 | 2004-05-01 | 2009-06-01 |  | 2022-05-01
Provision | 1998-03-01 | 2002-10-01 | 2010-07-01 |  |  |  |  | report saved under
Rescueboat (L. raft) | 1998-03-01 | 2002-05-01 | 2010-07-01
Rescueboat (Boat) | 1998-03-01 | 2002-05-01 | 2010-07-01
Liferaft | 1998-03-01 | 2002-05-01 | 2010-07-01
Freefallboat (PS) | 1998-03-01 | 2002-05-01 | 2009-06-01
Freefallboat (SB) | 1998-03-01 | 2002-05-01 | 2009-06-01 |  |  |  | date of last load test | result of the load test saved under |  | location
Facts & Figure
| Crane #1 |  | Crane #2 |  | Crane #3
Wires | Dia. in mm | Length in m | Dia. in mm | Length in m | Dia. in mm | Length in m
Luffing wire | 38 | 324 | 38 | 324 | 38 | 255
Hoisting wire | 68 | 197 | 68 | 197 | 50 | 200
Auxiliary hoist wire | 30 | 156 | 30 | 156 | 26 | 106
Wires | Dia. in mm | Length in m | SWL in mt
Provision | 10 | 45 | Crane #1 | 275 | Provision | 1.2
Rescueboat (Prov.) | 10 | 35 | Crane #2 | 275 | R.Boat (Prov.) | 0.99
Rescueboat (Boat) | 12 | 30 | Crane #3 | 150 | R.Boat (Boat) | 2.1
Liferaft | 14 | 28 | Aux. Hoist #1 | 32 | Liferaft | 2.1
Freefallboat (PS) | 16 | 26.34 | Aux. Hoist #2 | 32 | Freefallboat | 2x2,3
Freefallboat (SB) | 16 | 24.64 | Aux. Hoist #3 | 10
Remarks: | 07/2012 - New stander for aux. Hoist #1
Bohrung Kausche Hilfshub 1 + 2 |  | = 72 mm
Date: | 2012-07-16
Note on F11: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: @ Norderwerft / Seil-Hering
Note on F12: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: @ Norderwerft / Seil-Hering
Note on F13: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: @ Norderwerft / Seil-Hering
Note on F16: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: @ Norderwerft / Seil-Hering
Note on F18: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: @ Norderwerft / Seil-Hering

## Grietje
M/V Grietje (NB 1161 / Type 161a)
Change of crane wires |  |  |  |  | Date of commissioning: | 2000-02-01
[7 empty] | date of last inspection | kind/result of inspection - comments | wire replacement planned |  | done | next suggested inspection
Crane #1 | initial | 1st replacement | 2nd replacement | 3rd replacement | 4th replacement | 5th replacment |  |  | when | where | done
Luffing wire | 2000-01-01 | 2006-03-01 | 2011-04-01 | 2016-01-01
Hoisting wire | 2000-01-01 | 2006-03-01 | 2010-05-01 | 2016-01-01
Aux. wire | 2000-01-01 | 2008-07-01 |  | 2016-01-01
Crane #2
Luffing wire | 2000-01-01 | 2006-03-01 | 2010-10-01 | 2016-01-01
Hoisting wire | 2000-01-01 | 2006-03-01 | 2010-10-01 | 2011-07-01 | 2016-01-01
Aux. wire | 2000-01-01 | 2004-05-01 | 2005-07-01 | 2010-10-01 | 2016-01-01
Crane #3
Luffing wire | 2000-01-01 | 2006-03-01 | 2010-10-01 | 2016-01-01
Hoisting wire | 2000-01-01 | 2006-03-01 | 2010-10-01 | 2016-01-01
Aux. wire | 2000-01-01 | 2004-02-01 | 2011-10-01 | 2016-01-01
Provision | 2000-01-01 | 2004-04-01 | 2008-09-01 | 2013-09-01 |  |  |  | report saved under
Rescueboat (L. raft) | 2000-01-01 | 2004-04-01 | 2008-09-01 | 2013-09-01
Rescueboat (Boat) | 2000-01-01 | 2004-04-01 | 2008-09-01 | 2013-09-01
Liferaft | 2000-01-01 | 2004-04-01 | 2008-09-01 | 2013-09-01
Freefallboat (PS) | 2000-01-01 | 2004-04-01 | 2008-09-01 | 2013-09-01
Freefallboat (SB) | 2000-01-01 | 2004-04-01 | 2008-09-01 | 2013-09-01 |  |  | date of last load test | result of the load test saved under |  | location
Facts & Figure
| Crane #1 |  | Crane #2 |  | Crane #3
Wires | Dia. in mm | Length in m | Dia. in mm | Length in m | Dia. in mm | Length in m
Luffing wire | 44 | 293 | 44 | 293 | 38 | 289
Hoisting wire | 72 | 205 | 72 | 205 | 58 | 186
Auxiliary hoist wire | 32 | 156 | 32 | 156 | 30 | 156
Wires | Dia. in mm | Length in m | SWL in mt
Provision | 10 | 45 | Crane #1 | 320 | Provision | 1
Rescueboat (Prov.) | 10 | 35 | Crane #2 | 320 | R.Boat (Prov.) | 0.99
Rescueboat (Boat) | 12 | 30 | Crane #3 | 200 | R.Boat (Boat) | 2.1
Liferaft | 14 | 30 | Aux. Hoist #1 | 40 | Liferaft | 2.1
Freefallboat (PS) | 16 | 25.1 | Aux. Hoist #2 | 40 | Freefallboat | 2x2,3
Freefallboat (SB) | 16 | 26.8 | Aux. Hoist #3 | 32
Remarks:
Date: | 2016-01-29 |  |  |  | checked: | 2011-10-03

## Annegret
M/V Annegret (NB 1162 / Type 161a)
Change of crane wires |  |  |  |  | Date of commissioning: | 2000-03-01
[7 empty] | date of last inspection | kind/result of inspection - comments | wire replacement planned |  | done | next suggested inspection
Crane #1 | initial | 1st replacement | 2nd replacement | 3rd replacement | 4th replacement | 5th replacment |  |  | when | where | done
Luffing wire | 2000-02-01 | 2005-06-01 | 2010-03-01 | 2014-12-01
Hoisting wire | 2000-02-01 | 2005-06-01 | 2010-03-01 | 2014-12-01 | 2022-11-01
Aux. wire | 2000-02-01 | 2005-09-01 | 2010-03-01 | 2014-12-01 | 2022-11-01
Crane #2
Luffing wire | 2000-02-01 | 2005-06-01 | 2010-03-01 | 2015-05-01
Hoisting wire | 2000-02-01 | 2005-06-01 | 2007-05-01 | 2013-04-01 | 2014-12-01 | 2022-11-01
Aux. wire | 2000-02-01 |  | 2010-01-01 | 2014-12-01 | 2022-11-01
Crane #3
Luffing wire | 2000-02-01 | 2005-06-01 | 2010-03-01 | 2014-07-01
Hoisting wire | 2000-02-01 | 2005-06-01 | 2010-03-01 | 2014-12-01
Aux. wire | 2000-02-01 | 2009-06-01 |  | 2014-12-01 | 2022-11-01
Provision | 2000-02-01 | 2004-04-01 | 2008-11-01 | 2014-12-01 |  |  |  | report saved under
Rescueboat (L. raft) | 2000-02-01 | 2004-04-01 | 2008-11-01 | 2014-12-01
Rescueboat (Boat) | 2000-02-01 | 2004-04-01 | 2008-11-01 | 2014-12-01
Liferaft | 2000-02-01 | 2004-04-01 | 2008-11-01 | 2014-12-01
Freefallboat (PS) | 2000-02-01 | 2004-04-01 | 2009-06-01 | 2014-12-01
Freefallboat (SB) | 2000-02-01 | 2004-04-01 | 2009-06-01 | 2014-12-01 |  |  | date of last load test | result of the load test saved under |  | location
Facts & Figure
| Crane #1 |  | Crane #2 |  | Crane #3
Wires | Dia. in mm | Length in m | Dia. in mm | Length in m | Dia. in mm | Length in m
Luffing wire | 44 | 293 | 44 | 293 | 38 | 289
Hoisting wire | 72 | 205 | 72 | 205 | 58 | 186
Auxiliary hoist wire | 32 | 156 | 32 | 156 | 30 | 156
Wires | 2000-02-01: Dia. in mm; 2005-06-01: Length in m; 2007-05-01: SWL in mt
Provision | 10 | 45 | Crane #1 | 320 | Provision | 1
Rescueboat (Prov.) | 10 | 35 | Crane #2 | 320 | R.Boat (Raft) | 0.99
Rescueboat (Boat) | 12 | 30 | Crane #3 | 200 | R.Boat (Boat) | 2.1
Liferaft | 14 | 30 | Aux. Hoist #1 | 40 | Liferaft | 2.1
Freefallboat (PS) | 16 | 25.1 | Aux. Hoist #2 | 40 | Freefallboat | 2x2,3
Freefallboat (SB) | 16 | 26.8 | Aux. Hoist #3 | 32
Remarks: | 2000-02-01: 3rd replacement wire' - Hubseil Kran 1: Laufzeit nur bis 12/2018!! Siehe Kommentar in der Tabelle.
Date: | 2000-02-01: 2013-04-10; 2014-12-01: checked; 2022-11-01: 2015-05-10
Note on E7: Uwe Friedrich: Dieses ist der Draht, der in 04/2013 auf den Bahamas in Kran 2 eingezogen wurde. Er wurde während der Werftzeit in 2014 irrtümlich von Kran 2 abgetakelt und dann als neu in Kran 1 eingesetzt. Laufzeit deshalb nur noch bis 04/2018!!
Note on E11: Uwe Friedrich: in Antwerp / ABES by Seil-Hering and Crew.
Note on E12: Uwe Friedrich: During dry-docking @ Grand Bahama Shipyard
Note on F12: Uwe Friedrich: s. Kommentar Hubseil Kran 1 / 12/2014
Note on E16: Uwe Friedrich: Changed due to damage of wire sheave in Shanghai

## Paula
M/V Paula (NB 1174 / Type 161a)
Change of crane wires |  |  |  |  | Date of commissioning: | 2000-06-01
[7 empty] | date of last inspection | kind/result of inspection - comments | wire replacement planned |  | done | next suggested inspection
Crane #1 | initial | 1st replacement | 2nd replacement | 3rd replacement | 4th replacement | 5th replacment |  |  | when | where | done
Luffing wire | 2000-05-01 | 2005-08-01 | 2010-09-01 | 2015-06-01
Hoisting wire | 2000-05-01 | 2005-08-01 | 2010-09-01 | 2015-06-01
Aux. wire | 2000-05-01 |  | 2010-09-01 | 2015-06-01
Crane #2
Luffing wire | 2000-05-01 | 2005-08-01 | 2010-09-01 | 2015-06-01
Hoisting wire | 2000-05-01 | 2005-08-01 | 2009-02-01 | 2009-03-01 | 2015-06-01
Aux. wire | 2000-05-01 | 2004-06-01 | 2010-09-01 | 2015-06-01
Crane #3
Luffing wire | 2000-05-01 | 2005-08-01 | 2010-09-01 | 2015-06-01
Hoisting wire | 2000-05-01 | 2005-08-01 | 2010-09-01 | 2015-06-01
Aux. wire | 2000-05-01 |  | 2010-09-01 | 2015-06-01
Provision | 2000-05-01 | 2004-05-01 | 2007-09-01 |  |  |  |  | report saved under
Rescueboat (L. raft) | 2000-05-01 | 2004-05-01 | 2008-11-01
Rescueboat (Boat) | 2000-05-01 | 2004-05-01 | 2008-11-01
Liferaft | 2000-05-01 | 2004-05-01 | 2008-11-01
Freefallboat (PS) | 2000-05-01 | 2004-05-01 | 2008-11-01
Freefallboat (SB) | 2000-05-01 | 2004-05-01 | 2008-11-01 |  |  |  | date of last load test | result of the load test saved under |  | location
Facts & Figure
| Crane #1 |  | Crane #2 |  | Crane #3
Wires | Dia. in mm | Length in m | Dia. in mm | Length in m | Dia. in mm | Length in m
Luffing wire | 44 | 293 | 44 | 293 | 38 | 289
Hoisting wire | 72 | 205 | 72 | 205 | 58 | 186
Auxiliary hoist wire | 32 | 156 | 32 | 156 | 30 | 156
Wires | Dia. in mm | Length in m | SWL in mt
Provision | 10 | 45 | Crane #1 | 320 | Provision | 1
Rescueboat (Prov.) | 10 | 35 | Crane #2 | 320 | R.Boat (Raft) | 0.99
Rescueboat (Boat) | 12 | 30 | Crane #3 | 200 | R.Boat (Boat) | 2.1
Liferaft | 14 | 30 | Aux. Hoist #1 | 40 | Liferaft | 2.1
Freefallboat (PS) | 16 | 25.1 | Aux. Hoist #2 | 40 | Freefallboat | 2x2,3
Freefallboat (SB) | 16 | 26.8 | Aux. Hoist #3 | 32
Remarks:
Hoisting wire #2 was replaced by a smaller wire during project in Kakinada in 02/09.
Original wire was installed in Germany in 03/09.
Date: | 2015-07-10 |  |  |  | checked:
Note on E8: Uwe Friedrich: w/o pennant
Note on E13: Uwe Friedrich: incl. Pennant but w/o swivel
Note on E18: Uwe Friedrich: incl. Pennant but w/o swivel

## Wiebke
M/V Wiebke (NB 1175 / Type 161a)
Change of crane wires |  |  |  |  | Date of commissioning: | 2000-09-01
[7 empty] | date of last inspection | kind/result of inspection - comments | wire replacement planned |  | done | next suggested inspection
Crane #1 | initial | 1st replacement | 2nd replacement | 3rd replacement | 4th replacement | 5th replacment |  |  | when | where | done
Luffing wire | 2000-08-01 | 2005-12-01 | 2009-12-01 | 2015-10-01
Hoisting wire | 2000-08-01 | 2004-10-01 | 2009-12-01 | 2013-11-01 | 2020-12-01 |  | 2019-01-01 | NDT - no indications of significance were found
Aux. wire | 2000-08-01 |  |  | 2015-10-01
Crane #2
Luffing wire | 2000-08-01 | 2005-12-01 | 2009-12-01 | 2015-10-01
Hoisting wire | 2000-08-01 | 2005-12-01 | 2008-08-01 | 2013-11-01 | 2020-12-01 |  | 2019-01-01 | NDT - no indications of significance were found
Aux. wire | 2000-08-01 | 2005-04-01 |  | 2015-10-01
Crane #3
Luffing wire | 2000-08-01 | 2005-12-01 | 2009-12-01 | 2015-10-01
Hoisting wire | 2000-08-01 | 2005-12-01 | 2009-12-01 | 2015-10-01
Aux. wire | 2000-08-01 |  |  | 2015-10-01
Provision | 2000-08-01 | 2004-07-01 | 2009-04-01 |  |  |  |  | report saved under
[7 empty] | 2019-01-01 | G:\Heavylift\2-Service Reports\140.5_Wiebke\cranes
Rescueboat (L. raft) | 2000-08-01 | 2004-07-01 | 2009-04-01 | 2013-10-01
Rescueboat (Boat) | 2000-08-01 | 2004-07-01 | 2009-04-01 | 2013-10-01
Liferaft | 2000-08-01 | 2004-07-01 | 2009-12-08 | 2015-10-01
Freefallboat (PS) | 2000-08-01 | 2004-07-01 | 2008-12-14
Freefallboat (SB) | 2000-08-01 | 2004-07-01 | 2008-12-14 |  |  |  | date of last load test | result of the load test saved under |  | location
Facts & Figure
| Crane #1 |  | Crane #2 |  | Crane #3
Wires | Dia. in mm | Length in m | Dia. in mm | Length in m | Dia. in mm | Length in m
Luffing wire | 44 | 293 | 44 | 293 | 38 | 289
Hoisting wire | 72 | 205 | 72 | 205 | 58 | 186
Auxiliary hoist wire | 32 | 156 | 32 | 156 | 30 | 156
Wires | Dia. in mm | Length in m | SWL in mt
Provision | 10 | 45 | Crane #1 | 320 | Provision | 1
Rescueboat (Prov.) | 10 | 35 | Crane #2 | 320 | R.Boat (Raft) | 0.99
Rescueboat (Boat) | 12 | 30 | Crane #3 | 200 | R.Boat (Boat) | 2.1
Liferaft | 14 | 30 | Aux. Hoist #1 | 40 | Liferaft | 2.1
Freefallboat (PS) | 16 | 25.1 | Aux. Hoist #2 | 40 | Freefallboat | 2x2,3
Freefallboat (SB) | 16 | 26.8 | Aux. Hoist #3 | 32
Remarks:
Date: | 2014-01-13 |  |  |  | checked: | 2011-10-03
Note on E6: Uwe Friedrich: @ BREDO
Note on C7: Uwe Friedrich: Runner wurde aus Erstlieferung genommen (Reservedraht)
Note on E7: Uwe Friedrich: @BREDO due to wear and tear
Note on E8: Uwe Friedrich: @ BREDO
Note on E11: Uwe Friedrich: @ BREDO
Note on E12: Uwe Friedrich: @BREDO
Note on E13: Uwe Friedrich: @ BREDO
Note on E16: Uwe Friedrich: @ BREDO
Note on E17: Uwe Friedrich: @ BREDO
Note on E18: Uwe Friedrich: @ BREDO
Note on E25: Uwe Friedrich: @ BREDO

## Annette
M/V Annette (NB 1137 / Type 161b)
Change of crane wires |  |  |  |  | Date of commissioning: | 2003-12-01
[7 empty] | date of last inspection | kind/result of inspection - comments | wire replacement planned |  | done | next suggested inspection
Crane #1 | initial | 1st replacement | 2nd replacement | 3rd replacement | 4th replacement | 5th replacment |  |  | when | where | done
Luffing wire | 2003-11-01 | 2009-01-01 | 2014-01-01 |  |  |  | 2018-11-27 | NDT - no indications of significance were found
Hoisting wire | 2003-11-01 | 2007-11-01 | 2014-01-01 | 2020-12-01 |  |  | 2018-11-27 | NDT - for comments please have a look at service report
Aux. wire | 2003-11-01 | 2009-01-01 | 2014-01-01 |  |  |  | 2020-12-14 | Hoisting wire / fixed point damaged / corroded | 2020-12-16 | BRV | X
Crane #2
Luffing wire | 2003-11-01 | 2009-01-01 | 2014-01-01 |  |  |  | 2018-11-27 | NDT - no indications of significance were found
Hoisting wire | 2003-11-01 | 2007-12-01 | 2014-01-01 | 2020-12-01 |  |  | 2018-11-27 | NDT - for comments please have a look at service report
Aux. wire | 2003-11-01 | 2009-01-01 | 2014-01-01 | 2019-10-01 |  |  | 2020-12-14 | Hoisting wire / fixed point damaged / corroded | 2020-12-16 | BRV | X
Crane #3
Luffing wire | 2003-11-01 | 2009-01-01 | 2014-01-01 |  |  |  | 2018-11-27 | NDT - no indications of significance were found
Hoisting wire | 2003-11-01 | 2009-01-01 | 2014-01-01 |  |  |  | 2018-11-27 | NDT - for comments please have a look at service report
Aux. wire | 2003-11-01 | 2009-01-01 | 2014-01-01
Provision | 2003-11-01 | 2008-09-01 | [5 empty] | report saved under
[7 empty] | 2018-11-27 | G:\Heavylift\2-Service Reports\148.5 Annette\crane wires\inspection 27.11.18
Rescueboat (L. raft) | 2003-11-01 | 2008-09-01 | 2018-07-01
Rescueboat (Boat) | 2003-11-01 | 2008-09-01 | 2018-07-01
Liferaft | 2003-11-01 | 2008-09-01 | 2018-07-01
Freefallboat (PS) | 2003-11-01 | 2008-09-01 | 2018-07-01
Freefallboat (SB) | 2003-11-01 | 2008-09-01 | 2018-07-01 |  |  |  | date of last load test | result of the load test saved under |  | location
Facts & Figure
| Crane #1 |  | Crane #2 |  | Crane #3
Wires | Dia. in mm | Length in m | Dia. in mm | Length in m | Dia. in mm | Length in m
Luffing wire | 48 | 327 | 48 | 327 | 48 | 284
Hoisting wire | 66 | 226 | 66 | 226 | 66 | 226
Auxiliary hoist wire | 32 | 167 | 32 | 167 | 32 | 167
Wires | Dia. in mm | Length in m | SWL in mt
Provision | 10 | 45 | Crane #1 | 350 | Provision | 1
Rescueboat (Prov.) | 10 | 35 | Crane #2 | 350 | R.Boat (Prov.) | 0.99
Rescueboat (Boat) | 12 | 30 | Crane #3 | 250 | R.Boat (Boat) | 2.1
Liferaft | 14 | 25 | Aux. Hoist #1 | 40 | Liferaft | 2.1
Freefallboat (PS) | 16 | 25.1 | Aux. Hoist #2 | 40 | Freefallboat | 2x2,3
Freefallboat (SB) | 16 | 26.8 | Aux. Hoist #3 | 40
Remarks:
Date: | 2014-01-20 |  |  |  | checked: | 2011-10-09
Note on D6: Uwe Friedrich: @Norderwerft
Note on D7: Uwe Friedrich: @Norderwerft
Note on D8: Uwe Friedrich: @Norderwerft
Note on D11: Uwe Friedrich: @Norderwerft
Note on D12: Uwe Friedrich: @Norderwerft
Note on D13: Uwe Friedrich: @Norderwerft
Note on D16: Uwe Friedrich: @Norderwerft
Note on D17: Uwe Friedrich: @Norderwerft
Note on D18: Uwe Friedrich: @Norderwerft

## Maria
M/V Maria (NB 1138 / Type 161b)
Change of crane wires |  |  |  |  | Date of commissioning: | 2004-01-01
[7 empty] | date of last inspection | kind/result of inspection - comments | wire replacement planned |  | done | next suggested inspection
Crane #1 | initial | 1st replacement | 2nd replacement | 3rd replacement | 4th replacement | 5th replacment |  |  | when | where | done
Luffing wire | 2003-12-01 | 2008-10-01 | 2013-04-01 | 2022-07-01 |  |  | 2019-05-01 | NDT - approved for safe use
Hoisting wire | 2003-12-01 | 2008-10-01 | 2013-04-01 | 2015-12-01 |  |  | 2019-05-01 | NDT - please have a look in the report | 2019-06-01
Aux. wire | 2003-12-01 | 2008-10-01 | 2013-04-01 | 2019-07-01
Crane #2
Luffing wire | 2003-12-01 | 2008-10-01 | 2013-04-01 | 2022-07-01 |  |  | 2019-05-01 | NDT - approved for safe use
Hoisting wire | 2003-12-01 | 2008-10-01 | 2013-04-01 | 2022-07-01 |  |  | 2019-05-01 | NDT - please have a look in the report
Aux. wire | 2003-12-01 | 2008-10-01 | 2013-04-01 | 2022-07-01
Crane #3
Luffing wire | 2003-12-01 | 2008-10-01 | 2013-04-01 |  |  |  | 2019-05-01 | NDT - approved for safe use
Hoisting wire | 2003-12-01 | 2008-10-01 | 2014-02-01 |  |  |  | 2019-05-01 | NDT - approved for safe use
Aux. wire | 2003-12-01 | 2008-10-01 | 2013-04-01 | 2015-06-01
Provision | 2003-12-01 | 2008-04-01 | 2020-05-01 |  |  |  |  | report saved under
[7 empty] | 2019-05-01 | G:\Heavylift\2-Service Reports\148.6 Maria\cranes
Rescueboat (L. raft) | 2003-12-01 | 2008-04-01 | 2018-04-01
Rescueboat (Boat) | 2003-12-01 | 2008-04-01 | 2018-04-01
Liferaft | 2003-12-01 | 2008-04-01 | 2018-04-01
Freefallboat (PS) | 2003-12-01 | 2008-04-01 | 2018-04-01
Freefallboat (SB) | 2003-12-01 | 2008-04-01 | 2018-04-01 |  |  |  | date of last load test | result of the load test saved under |  | location
Facts & Figure
| Crane #1 |  | Crane #2 |  | Crane #3
Wires | Dia. in mm | Length in m | Dia. in mm | Length in m | Dia. in mm | Length in m
Luffing wire | 48 | 327 | 48 | 327 | 48 | 284
Hoisting wire | 66 | 226 | 66 | 226 | 66 | 226
Auxiliary hoist wire | 32 | 167 | 32 | 167 | 32 | 167
Wires | Dia. in mm | Length in m | SWL in mt
Provision | 10 | 45 | Crane #1 | 350 | Provision | 1
Rescueboat (Prov.) | 10 | 35 | Crane #2 | 350 | R.Boat (Prov.) | 0.99
Rescueboat (Boat) | 12 | 30 | Crane #3 | 250 | R.Boat (Boat) | 2.1
Liferaft | 14 | 25 | Aux. Hoist #1 | 40 | Liferaft | 2.1
Freefallboat (PS) | 16 | 25.1 | Aux. Hoist #2 | 40 | Freefallboat | 2x2,3
Freefallboat (SB) | 16 | 26.8 | Aux. Hoist #3 | 40
Remarks:
Date: | 2013-07-09 |  |  |  | checked: | 2011-10-09
Note on D6: Uwe Friedrich: 03/13 Norderwerft
Note on D7: Uwe Friedrich: 03/13 Norderwerft
Note on E7: Uwe Friedrich: R'dam due to Stevedores damage in Victoria / BC.
Note on D8: Uwe Friedrich: 03/13 Norderwerft
Note on D11: Uwe Friedrich: 03/13 Norderwerft
Note on D12: Uwe Friedrich: 03/13 Norderwerft
Note on E12: Uwe Friedrich: R'dam due to Stevedores damage in Victoria / BC.
Note on D13: Uwe Friedrich: 03/13 Norderwerft
Note on D16: Uwe Friedrich: 03/13 Norderwerft
Note on D17: Uwe Friedrich: @Antwerpen, ABES n.v.
Note on D18: Uwe Friedrich: 03/13 Norderwerft

## Frauke
M/V Frauke (NB 1275 / Type 176)
Change of crane wires |  |  |  |  | Date of commissioning: | 2008-02-01
[7 empty] | date of last inspection | kind/result of inspection - comments | wire replacement planned |  | done | next suggested inspection
Crane #1 | initial | 1st replacement | 2nd replacement | 3rd replacement | 4th replacement | 5th replacment |  |  | when | where | done
Luffing wire | 2008-01-01 | 2013-05-01 | 2022-04-01 |  |  |  | 2018-02-01 | fit for further use
Hoisting wire | 2008-01-01 | 2013-05-01 | 2021-10-01 |  |  |  | 2018-02-01 | fit for further use
Aux. wire | 2008-01-01 | 2013-05-01 | 2013-11-01 | 2021-10-01
Trolley wires | 2008-01-01 | N/A
Crane #2
Luffing wire | 2008-01-01 | 2013-05-01 | 2022-04-01 |  |  |  | 2018-02-01 | fit for further use
Hoisting wire | 2008-01-01 | 2013-05-01 | 2021-10-01 |  |  |  | 2018-02-01 | fit for further use
Aux. wire | 2008-01-01 | 2013-05-01 | 2021-10-01
Trolley wires | 2008-01-01 | N/A
Crane #3
Luffing wire | 2008-01-01 | 2013-05-01 | 2021-10-01 |  |  |  | 2018-02-01 | fit for further use
Hoisting wire | 2008-01-01 | 2013-05-01 | 2022-04-01 |  |  |  | 2018-02-01 | fit for further use
Aux. wire | 2008-01-01 | 2013-05-01 | 2021-10-01
Provision | 2008-01-01 | 2013-01-01 | [5 empty] | report saved under
[7 empty] | 2018-02-01 | G:\Heavylift\2-Service Reports\150 Frauke\cranes
Rescueboat (L. raft) | 2008-01-01 | 2013-01-01
Rescueboat (Boat) | 2008-01-01 | 2013-01-01
Liferaft | 2008-01-01 | 2013-01-01
Freefallboat (PS) | 2008-01-01 | 2013-01-01
Freefallboat (SB) | 2008-01-01 | 2013-01-01 |  |  |  |  | date of last load test | result of the load test saved under |  | location
Facts & Figure
| Crane #1 |  | Crane #2 |  | Crane #3
Wires | Dia. in mm | Length in m | Dia. in mm | Length in m | Dia. in mm | Length in m
Luffing wire | 48 | 600 | 48 | 600 | 48 | 377
Hoisting wire | 66 | 490 | 66 | 490 | 66 | 334
Auxiliary hoist wire | 32 | 221 | 32 | 221 | 32 | 180
Trolley Hoisting | 30 | 168 | 30 | 168
Trolley forward | 28 | 85 | 28 | 85
Trolley backward | 28 | 57 | 28 | 57
Wires | Dia. in mm | Length in m | SWL in mt
Provision | 12 | 100 | Crane #1 | 700 | Provision | 3.5
Rescueboat (Prov.) | 12 | 34 | Crane #2 | 700 | R.boat (Prov.) | 2
Rescueboat (Boat) | 13 | 30 | Crane #3 | 350 | R.boat (boat) | 2.1
Liferaft | 14 | 30 | Aux. Hoist #1 | 60 | Liferaft | 2.1
Freefallboat (PS) | 16 | 31.2 | Aux. Hoist #2 | 60 | Freefallboat | 4,685 (2x2,35)
Freefallboat (SB) | 16 | 33.2 | Aux. Hoist #3 | 40
|  |  | Trolley #1 | 30 | Trolley #2 | 30
Remarks: | Tuggerwinch(es): | d = 18 mm ; l = 80,0 m
Date: | 2013-12-02 |  |  |  | checked: | 2011-10-16
Note on D6: Friedrich, Uwe: Esbjerg
Note on D8: Uwe Friedrich: Jinhae / Korea - defekt durch Seilscheibenschaden
Note on C9: Uwe Friedrich: Trolleys were dismantled during shipyard stay@Norderwerft in 05/2013
Note on D11: Friedrich, Uwe: Esbjerg
Note on C14: Uwe Friedrich: Trolleys were dismantled during shipyard stay@Norderwerft in 05/2013
Note on D17: Friedrich, Uwe: Esbjerg

## Anne-Sofie
M/V Anne-Sofie (NB 1276 / Type 176)
Change of crane wires |  |  |  |  | Date of commissioning: | 2008-04-01
[7 empty] | date of last inspection | kind/result of inspection - comments | wire replacement planned |  | done | next suggested inspection
Crane #1 | initial | 1st replacement | 2nd replacement | 3rd replacement | 4th replacement | 5th replacment |  |  | when | where | done
Luffing wire | 2008-03-01 | 2013-02-01 | 2021-07-01 |  |  |  | 2018-04-01 | NDT - no indications of significance were found
Hoisting wire | 2008-03-01 | 2013-02-01 | 2018-04-01 |  |  |  | 2018-04-01 | NDT - wire replaced
Aux. wire | 2008-03-01 | 2013-02-01 | 2021-07-01 |  |  |  | 2018-04-01 | NDT - no indications of significance were found
Trolley wires | 2008-03-01 | N/A | N/A
Crane #2
Luffing wire | 2008-03-01 | 2013-02-01 | 2022-03-01 |  |  |  | 2018-04-01 | NDT - no indications of significance were found
Hoisting wire | 2008-03-01 | 2013-02-01 | 2016-06-01 |  |  |  | 2018-04-01 | NDT - no indications of significance were found
Aux. wire | 2008-03-01 | 2013-02-01 | 2018-04-01 |  |  |  | 2018-04-01 | NDT - wire replaced
Trolley wires | 2008-03-01 | N/A | N/A
Crane #3
Luffing wire | 2008-03-01 | 2013-02-01 | 2021-07-01 |  |  |  | 2018-04-01 | NDT - no indications of significance were found
Hoisting wire | 2008-03-01 | 2013-02-01 | 2018-04-01 |  |  |  | 2018-04-01 | NDT - wire replaced
Aux. wire | 2008-03-01 | 2013-02-01 | 2021-07-01 |  |  |  | 2018-04-01 | NDT - no indications of significance were found
Provision | 2008-03-01 | 2013-02-01 | [5 empty] | report saved under
[7 empty] | 2018-04-01 | G:\Heavylift\Drydock\148.2 Anne-Sofie\2018 - Singapore\Franklin Offshore
Rescueboat (L. raft) | 2008-03-01 | 2013-02-01
Rescueboat (Boat) | 2008-03-01 | 2013-02-01
Liferaft | 2008-03-01 | 2013-02-01
Freefallboat (PS) | 2008-03-01 | 2013-02-01
Freefallboat (SB) | 2008-03-01 | 2013-02-01 |  |  |  |  | date of last load test | result of the load test saved under |  | location
Facts & Figure
| Crane #1 |  | Crane #2 |  | Crane #3
Wires | Dia. in mm | Length in m | Dia. in mm | Length in m | Dia. in mm | Length in m
Luffing wire | 48 | 600 | 48 | 600 | 48 | 377
Hoisting wire | 66 | 490 | 66 | 490 | 66 | 334
Auxiliary hoist wire | 32 | 221 | 32 | 221 | 32 | 180
Trolley Hoisting | 30 | 168 | 30 | 168
Trolley forward | 28 | 85 | 28 | 85
Trolley backward | 28 | 57 | 28 | 57
Wires | Dia. in mm | Length in m | SWL in mt
Provision | 12 | 100 | Crane #1 | 700 | Provision | 3.5
Rescueboat (Prov.) | 12 | 34 | Crane #2 | 700 | R.boat (Prov.) | 2
Rescueboat (Boat) | 13 | 30 | Crane #3 | 350 | R.boat (boat) | 2.1
Liferaft | 14 | 30 | Aux. Hoist #1 | 60 | Liferaft | 2.1
Freefallboat (PS) | 16 | 31.2 | Aux. Hoist #2 | 60 | Freefallboat | 4,685 (2x2,35)
Freefallboat (SB) | 16 | 33.2 | Aux. Hoist #3 | 40
|  |  | Trolley #1 | 30 | Trolley #2 | 30
Remarks: | Tuggerwinch(es): | d = 18 mm ; l = 80,0 m
Date: | 2011-03-23 |  |  |  | checked: | 2021-08-20
Note on D8: Friedrich, Uwe: This wire was taken from ship's stock
Note on C9: Uwe Friedrich: Trolleys were dismantled during shipyard stay in 02/2013.
Note on D12: Uwe Friedrich: @Abu Dhabi, due to wire sheave damage
Note on D13: Friedrich, Uwe: This wire was taken from ship's stock
Note on C14: Uwe Friedrich: Trolleys were dismantled during shipyard stay in 02/2013

## Trina
M/V Trina (NB 1277 / Type 176)
Change of crane wires |  |  |  |  | Date of commissioning: | 2008-11-01
[7 empty] | date of last inspection | kind/result of inspection - comments | wire replacement planned |  | done | next suggested inspection
Crane #1 | initial | 1st replacement | 2nd replacement | 3rd replacement | 4th replacement | 5th replacment |  |  | when | where | done
Luffing wire | 2008-10-01 | 2013-12-01 | 2022-06-01 |  |  |  | 2018-11-01 | NDT - no indications of significance were found
Hoisting wire | 2008-10-01 | 2013-12-01 | 2022-06-01 |  |  |  | 2018-11-02 | NDT - no indications of significance were found
Aux. wire | 2008-10-01 | 2012-11-01 | 2022-06-01 |  |  |  | 2018-11-03 | NDT - no indications of significance were found
Trolley wires | 2008-10-01 | N/A | N/A
Crane #2
Luffing wire | 2008-10-01 | 2013-12-01 | 2022-06-01 |  |  |  | 2018-11-01 | NDT - no indications of significance were found
Hoisting wire | 2008-10-01 | 2013-12-01 | 2022-06-01 |  |  |  | 2018-11-02 | NDT - no indications of significance were found
Aux. wire | 2008-10-01 | 2013-12-01 | 2022-06-01 |  |  |  | 2018-11-03 | NDT - no indications of significance were found
Trolley wires | 2008-10-01 | N/A | N/A
Crane #3
Luffing wire | 2008-10-01 | 2012-02-01 | 2022-06-01 |  |  |  | 2021-03-01 | Visual - no findings
Hoisting wire | 2008-10-01 | 2013-12-01 | 2022-06-01 |  |  |  | 2018-11-02 | NDT - no indications of significance were found
Aux. wire | 2008-10-01 | 2012-02-01 | 2022-06-01 |  |  |  | 2021-03-01 | Visual - no findings
Provision | 2008-10-01 | 2013-12-01 | [5 empty] | report saved under
[7 empty] | 2018-11-01 | G:\Heavylift\2-Service Reports\141 Trina\cranes
Rescueboat (L. raft) | 2008-10-01 | 2013-12-01 |  |  |  |  | 2021-03-01 | ..\..\02 Service Reports\141 Trina\crane wires\NDT\2021_03 Crane #3 Pfeifer
Rescueboat (Boat) | 2008-10-01 | 2013-12-01
Liferaft | 2008-10-01 | 2013-12-01
Freefallboat (PS) | 2008-10-01 | 2013-12-01
Freefallboat (SB) | 2008-10-01 | 2013-12-01 |  |  |  |  | date of last load test | result of the load test saved under |  | location
Facts & Figure
| Crane #1 |  | Crane #2 |  | Crane #3
Wires | Dia. in mm | Length in m | Dia. in mm | Length in m | Dia. in mm | Length in m
Luffing wire | 48 | 600 | 48 | 600 | 48 | 377
Hoisting wire | 66 | 490 | 66 | 490 | 66 | 334
Auxiliary hoist wire | 32 | 221 | 32 | 221 | 32 | 180
Trolley Hoisting | 30 | 168 | 30 | 168
Trolley forward | 28 | 85 | 28 | 85
Trolley backward | 28 | 57 | 28 | 57
Wires | Dia. in mm | Length in m | SWL in mt
Provision | 12 | 100 | Crane #1 | 700 | Provision | 3.5
Rescueboat (Prov.) | 12 | 34 | Crane #2 | 700 | R.boat (Prov.) | 2
Rescueboat (Boat) | 13 | 30 | Crane #3 | 350 | R.boat (boat) | 2.1
Liferaft | 12 | 30 | Aux. Hoist #1 | 60 | Liferaft | 1.428
Freefallboat (PS) | 16 | 31.2 | Aux. Hoist #2 | 60 | Freefallboat | 4,685 (2x2,35)
Freefallboat (SB) | 16 | 33.2 | Aux. Hoist #3 | 40
|  |  | Trolley #1 | 30 | Trolley #2 | 30
Remarks: | Tuggerwinch(es): | d = 18 mm ; l = 80,0 m
Date: | 2013-12-18 |  |  |  | checked: | 2012-11-05
Note on C8: Uwe Friedrich: La Rochelle, due to damage
Note on C9: Uwe Friedrich: Dismantled during shipyard stay 12/2013 Norderwerft
Note on C14: Uwe Friedrich: Dismantled during shipyard stay 12/2013 Norderwerft
Note on C16: Uwe Friedrich: Norderwerft during re-fitting the foundation bearing of the jib, due to heavy corrosion
Note on C18: Uwe Friedrich: Norderwerft during re-fitting the foundation bearing of the jib, due to heavy corrosion

## Regine
M/V Regine (NB 1278 / Type 176)
Change of crane wires |  |  |  |  | Date of commissioning: | 2009-02-01
[7 empty] | date of last inspection | kind/result of inspection - comments | wire replacement planned |  | done | next suggested inspection
Crane #1 | initial | 1st replacement | 2nd replacement | 3rd replacement | 4th replacement | 5th replacment |  |  | when | where | done
Luffing wire | 2009-01-01 | 2014-01-01 | 2022-06-01 |  |  |  | 2019-03-01 | fit for use across the areas covered by the report
Hoisting wire | 2009-01-01 | 2014-01-01 | 2022-06-01 |  |  |  | 2019-03-01 | fit for use across the areas covered by the report
Aux. wire | 2009-01-01 | 2012-12-01 | 2021-12-01
Trolley wires | 2009-01-01 | 2014-01-01
Crane #2
Luffing wire | 2009-01-01 | 2014-01-01 | 2022-06-01 |  |  |  | 2019-03-01 | fit for use across the areas covered by the report
Hoisting wire | 2009-01-01 | 2014-01-01 | 2022-06-01 |  |  |  | 2019-03-01 | fit for use across the areas covered by the report
Aux. wire | 2009-01-01 | 2014-01-01 | 2022-06-01
Trolley wires | 2009-01-01 | 2014-01-01
Crane #3
Luffing wire | 2009-01-01 | 2014-01-01 | 2022-06-01 |  |  |  | 2019-03-01 | fit for use across the areas covered by the report
Hoisting wire | 2009-01-01 | 2014-01-01 | 2022-06-01 |  |  |  | 2019-03-01 | fit for use across the areas covered by the report
Aux. wire | 2009-01-01 | 2014-01-01 | 2022-06-01
Provision | 2009-01-01 | 2014-09-01 | 2019-03-01 |  |  |  |  | report saved under
[7 empty] | 2019-03-01 | G:\Heavylift\2-Service Reports\142 Regine\cranes\2019-03-18 Hendrik Veder (Hamburg) wire inspection
Rescueboat (L. raft) | 2009-01-01 |  | 2019-03-01
Rescueboat (Boat) | 2009-01-01 |  | 2019-03-01
Liferaft | 2009-01-01 |  | 2019-03-01
Freefallboat (PS) | 2009-01-01 |  | 2019-03-01
Freefallboat (SB) | 2009-01-01 |  | 2019-03-01 |  |  |  | date of last load test | result of the load test saved under |  | location
Facts & Figure
| Crane #1 |  | Crane #2 |  | Crane #3
Wires | Dia. in mm | Length in m | Dia. in mm | Length in m | Dia. in mm | Length in m
Luffing wire | 48 | 600 | 48 | 600 | 48 | 377
Hoisting wire | 66 | 490 | 66 | 490 | 66 | 334
Auxiliary hoist wire | 32 | 221 | 32 | 221 | 32 | 180
Trolley Hoisting | 30 | 168 | 30 | 168
Trolley forward | 28 | 85 | 28 | 85
Trolley backward | 28 | 57 | 28 | 57
Wires | Dia. in mm | Length in m | SWL in mt
Provision | 12 | 100 | Crane #1 | 700 | Provision | 3.5
Rescueboat (Prov.) | 12 | 34 | Crane #2 | 700 | R.boat (Prov.) | 2
Rescueboat (Boat) | 13 | 30 | Crane #3 | 350 | R.boat (boat) | 2.1
Liferaft | 12 | 30 | Aux. Hoist #1 | 60 | Liferaft | 1.428
Freefallboat (PS) | 16 | 31.2 | Aux. Hoist #2 | 60 | Freefallboat | 4,685 (2x2,35)
Freefallboat (SB) | 16 | 33.2 | Aux. Hoist #3 | 40
|  |  | Trolley #1 | 30 | Trolley #2 | 30
Remarks: | Tuggerwinch(es): | d = 18 mm ; l = 80,0 m
Date: | 2022-06-30 |  |  |  | checked
Note on D6: Friedrich, Uwe: Bremerhaven, while stay for ME Silencer exchange ("Alte Banane")
Note on C8: Uwe Friedrich: In R'dam wg. Beschädigung durch Abspringen der Seilscheibe
Note on D8: Friedrich, Uwe: Rostock, due to damage

## Svenja
M/V Svenja (NB 1279 / Type 183)
Change of crane wires |  |  |  |  | Date of commissioning: | 2010-12-01
[7 empty] | date of last inspection | kind/result of inspection - comments | wire replacement planned |  | done | next suggested inspection
Crane #1 | initial | 1st replacement | 2nd replacement | 3rd replacement | 4th replacement | 5th replacment |  |  | when | where | done
Luffing wire | 2010-11-01 | 2015-12-01 |  |  |  |  | 2021-02-01 | Next MRT should be conducted within 12 months
Hoisting wire | 2010-11-01 | 2015-12-01 |  |  |  |  | 2021-02-01 | Next MRT should be conducted within 12 months
Aux. wire | 2010-11-01 | 2015-12-01
Crane #2
Luffing wire | 2010-11-01 | 2015-12-01 |  |  |  |  | 2021-02-01 | Next MRT should be conducted within 12 months
Hoisting wire | 2010-11-01 | 2015-12-01 | 2021-03-01
Aux. wire | 2010-11-01 | 2015-12-01
Provision | 2010-11-01 | 2015-12-01 | [5 empty] | report saved under
Rescueboat (L. raft) | 2010-11-01 | 2015-12-01
Rescueboat (Boat) | 2010-11-01 | 2015-12-01
Liferaft | 2010-11-01 | 2015-12-01
Freefallboat (PS) | 2010-11-01 | 2015-12-01
Freefallboat (SB) | 2010-11-01 | 2015-12-01 |  |  |  |  | date of last load test | result of the load test saved under |  | location
Facts & Figure
| Crane #1 |  | Crane #2
Wires | Dia. in mm | Length in m | Dia. in mm | Length in m
Luffing wire | 66 | 503 | 66 | 503
Hoisting wire | 72 | 740 | 72 | 740
Auxiliary hoist wire | 36 | 194 | 36 | 194
Sling hoist wire | 26 | 135 | 26 | 135
Tugger winches | 18 | 2x 120,0 | 18 | 2x 120,0
Wires | Dia. in mm | Length in m | SWL in mt
Provision | 13 | 90 | Crane #1 | 1000 | Provision | 3.5
Rescueboat (Prov.) | 12 | 34 | Crane #2 | 1000 | R.Boat (Prov.) | 2
Rescueboat (Boat) | 13 | 30 | Aux. Hoist #1 | 60 | R.Boat (Boat) | 2.1
Liferaft | 12 | 30 | Aux. Hoist #2 | 60 | Liferaft | 1.52
Freefallboat (PS) | 16 | 31.15 | Sling Hoist #1 | 10 | Freefallboat | 5.53
Freefallboat (SB) | 16 | 33.3 | Sling Hoist #2 | 10
Remarks:
Date: | 2015-12-16 |  |  |  | checked: | 2012-01-25
Note on D12: [Kommentarthread] Ihre Version von Excel gestattet Ihnen das Lesen dieses Kommentarthreads. Jegliche Bearbeitungen daran werden jedoch entfernt, wenn die Datei in einer neueren Version von Excel geöffnet wird. Weitere Informationen: https://go.microsoft.com/fwlink/?linkid=870924. Kommentar: R'dam: Due to mechanical damage, caused by...?

## Lone
M/V Lone (NB 1280 / Typ 183)
Change of crane wires |  |  |  |  | Date of commissioning: | 2011-03-01
[7 empty] | date of last inspection | kind/result of inspection - comments | wire replacement planned |  | done | next suggested inspection
Crane #1 | initial | 1st replacement | 2nd replacement | 3rd replacement | 4th replacement | 5th replacment |  |  | when | where | done
Luffing wire | 2011-02-01 | 2016-02-01
Hoisting wire | 2011-02-01 | 2016-02-01
Aux. wire | 2011-02-01 | 2016-02-01
Crane #2
Luffing wire | 2011-02-01 | 2016-02-01
Hoisting wire | 2011-02-01 | 2016-02-01
Aux. wire | 2011-02-01 | 2016-02-01
Provision | 2011-02-01 | 2016-02-01 | [5 empty] | report saved under
Rescueboat (L. raft) | 2011-02-01 | 2016-02-01
Rescueboat (Boat) | 2011-02-01 | 2016-02-01
Liferaft | 2011-02-01 | 2016-02-01
Freefallboat (PS) | 2011-02-01 | 2016-02-01
Freefallboat (SB) | 2011-02-01 | 2016-02-01 |  |  |  |  | date of last load test | result of the load test saved under |  | location
Facts & Figure
| Crane #1 |  | Crane #2
Wires | Dia. in mm | Length in m | Dia. in mm | Length in m
Luffing wire | 66 | 503 | 66 | 503
Hoisting wire | 72 | 740 | 72 | 740
Auxiliary hoist wire | 36 | 194 | 36 | 201
Sling hoist wire | 26 | 135 | 26 | 135
Tugger winches | 18 | 2x 120,0 | 18 | 2x 120,0
Wires | Dia. in mm | Length in m | SWL in mt
Provision | 13 | 90 | Crane #1 | 1000 | Provision | 3.5
Rescueboat (Prov.) | 12 | 34 | Crane #2 | 1000 | R.Boat (Prov.) | 2
Rescueboat (Boat) | 13 | 30 | Aux. Hoist #1 | 60 | R.Boat (Boat) | 2.1
Liferaft | 12 | 30 | Aux. Hoist #2 | 60 | Liferaft | 1.52
Freefallboat (PS) | 16 | 31.15 | Sling Hoist #1 | 10 | Freefallboat | 5.53
Freefallboat (SB) | 16 | 33.3 | Sling Hoist #2 | 10
Date: | 2016-03-31 |  |  |  | checked: | 2012-01-25
Note on E30: Uwe Friedrich: Achtung: Unterschiedliche Seillänge!